## Summary
Story | SPM-30: As an Event Operations Manager, I want to assign an Event Coordinator to an event so that there is a clear person responsible for coordinating it
Sheet | Test Case ID | Title | Linked AC | Type | Source | Status | Superseded by | Change #
TC01 | SPM-30-TC01 | Assignments page lists only submitted events with no coordinator | AC2 | Positive | Acceptance Criteria | Updated |  | Week 7 #5
TC02 | SPM-30-TC02 | Ops Manager dashboard 'Awaiting assignment' shows unassigned submitted events | AC2 | Positive | Code | Updated |  | Week 7 #5
TC03 | SPM-30-TC03 | Non-Ops-Manager roles cannot open the Assignments page | AC1, AC2 | Negative | Acceptance Criteria | Updated |  | Week 7 #5
TC04 | SPM-30-TC04 | Coordinator dropdown only lists Event Coordinators | AC1 | Negative | Acceptance Criteria | Updated |  | Week 7 #5
TC05 | SPM-30-TC05 | Assign cannot be completed without choosing a coordinator | AC1 | Negative | Acceptance Criteria | Active
TC06 | SPM-30-TC06 | Organiser sees 'Not yet assigned' before a coordinator is assigned | AC5 | Boundary | Code | Active
TC07 | SPM-30-TC07 | Coordinators cannot manage an event that has no coordinator yet | AC4 | Negative | Acceptance Criteria | Active
TC08 | SPM-30-TC08 | Ops Manager assigns a coordinator; it is recorded and the event moves to Under review | AC1, AC2, AC3 | Positive | Acceptance Criteria | Active
TC09 | SPM-30-TC09 | Assigned coordinator sees and can manage the event | AC4 | Positive | Acceptance Criteria | Active
TC10 | SPM-30-TC10 | Owning organiser sees the assigned coordinator | AC5 | Positive | Acceptance Criteria | Active
TC11 | SPM-30-TC11 | Organiser from the same company sees the assigned coordinator | AC5 | Positive | Acceptance Criteria | Active
TC12 | SPM-30-TC12 | Attendee does not see the assigned coordinator | AC5 | Negative | Code | Active
TC13 | SPM-30-TC13 | Ops Manager reassigns an event from the event page | AC6, AC3 | Positive | Acceptance Criteria | Active
TC14 | SPM-30-TC14 | After reassignment the previous coordinator loses access and the new one gains it | AC6, AC4 | Positive | Acceptance Criteria | Active
TC15 | SPM-30-TC15 | Ops Manager reassigns an event from the Assignments page | AC6, AC3 | Positive | Acceptance Criteria | Updated |  | Week 7 #5
TC16 | SPM-30-TC16 | Confirmed and Postponed events can be reassigned | AC6 | Boundary | Acceptance Criteria | Active
TC17 | SPM-30-TC17 | Completed, Cancelled and Rejected events cannot be reassigned | AC6 | Negative | Acceptance Criteria | Updated |  | Week 7 #5
TC18 | SPM-30-TC18 | Reassigning to the currently assigned coordinator is not a change | AC6 | Boundary | Acceptance Criteria | Active
TC19 | SPM-30-TC19 | Coordinator and organiser cannot change the assigned coordinator | AC1, AC6 | Negative | Acceptance Criteria | Active
TC20 | SPM-30-TC20 | Empty state when no events are awaiting assignment | AC2 | Boundary | Acceptance Criteria | Active
AC | Acceptance Criterion |  |  | Covered by
AC1 | An authorised user can assign a coordinator to an event. |  |  | SPM-30-TC03 SPM-30-TC04 SPM-30-TC05 SPM-30-TC08 SPM-30-TC19
AC2 | The Event Operations Manager can view or filter submitted events that do not yet have an assigned coordinator. |  |  | SPM-30-TC01 SPM-30-TC02 SPM-30-TC03 SPM-30-TC08 SPM-30-TC20
AC3 | The assigned coordinator is recorded against the event. |  |  | SPM-30-TC08 SPM-30-TC13 SPM-30-TC15
AC4 | The assigned coordinator can view and manage the event. |  |  | SPM-30-TC07 SPM-30-TC09 SPM-30-TC14
AC5 | The Event Organiser can see the assigned coordinator where appropriate. |  |  | SPM-30-TC06 SPM-30-TC10 SPM-30-TC11 SPM-30-TC12
AC6 | An event can be reassigned to another coordinator. |  |  | SPM-30-TC13 SPM-30-TC14 SPM-30-TC15 SPM-30-TC16 SPM-30-TC17 SPM-30-TC18 SPM-30-TC19
Code reviewed | src/app/assignments/page.tsx design/mockups/AssignmentQueue.dc.html src/lib/permissions.ts src/lib/roles.ts docs/PERMISSIONS.md src/app/api/events/[id]/route.ts src/app/events/[id]/page.tsx src/app/events/[id]/EventGlance.tsx src/app/dashboard/page.tsx src/app/events/page.tsx prisma/schema.prisma prisma/seed.ts scripts/seed-spm30.ts docs/discussions/20260916 - IS212-2026-discussions.md

## Open Questions (hidden)
# | Question / ambiguity for the PO or developer | Answer
1 | NOTE: Test data comes from scripts/seed-spm30.ts (npm run fixtures:spm30). It only deletes and recreates events whose seed key starts with 'spm30_'; the rest of the database is untouched. Run it before a full pass, and wherever a case's 'Data reset' line says to.
2 | NOTE: TC20 (empty state) needs zero unassigned submitted events in the whole database, which on the shared database means assigning base-seed events such as 'Nusantara Developer Summit'. The fixture script does not restore those. Run TC20 on a Neon branch or local database.
3 | NOTE: Organisers from an unrelated company not seeing the event is covered by SPM-31 (visibility), so it is not repeated here.
4 | OPEN: Notifications are written on assignment (new coordinator) and reassignment (new and previous coordinator), but there are no test cases for them yet because the Notifications page (S-04, SPM-53) is still a placeholder. Add them once SPM-53 is built.

## TC01
v2 (2026-10-20): The Event Operations Manager is now shown as the 'Event Coordinator Lead' (SPM-84 AC1, forum #129, Week 7 Change #5) - the same role, accounts, permissions and pages. Read 'Operations Manager', 'Event Operations Manager' or 'Ops Manager' in this case as 'Event Coordinator Lead'; on screen the role is shown under its new name, and refusals say 'Assigning coordinators is the Event Coordinator Lead's role.'
Item
Test Case ID | SPM-30-TC01
Pre-conditions | Test data freshly loaded: run `npm run fixtures:spm30` from the project folder just before this case. Logged in as Grace Lim (grace.lim@connectsphere.com / password123), Event Operations Manager.
Test Steps | 1. Click 'Assignments' in the sidebar 2. Click 'SPM30 Meridian Graduate Evening' in the list to open it
Test Data | Expected rows include: SPM30 Nusantara Developer Meetup, SPM30 Meridian Graduate Evening ¦ Must not appear: SPM30 Kirana Regional Offsite (Under review, Priya Raj), SPM30 Draft Investor Update (Draft)
Expected Result | The 'Awaiting assignment' table shows 'SPM30 Nusantara Developer Meetup' and 'SPM30 Meridian Graduate Evening' with their client, date and how long they have been waiting. Base-seed events that are also submitted with no coordinator (e.g. 'Nusantara Developer Summit', 'Meridian Graduate Recruitment Evening') may appear too. 'SPM30 Kirana Regional Offsite' (already has a coordinator) is not listed. 'SPM30 Draft Investor Update' (draft) is not listed. The opened event's page shows the 'Submitted' status badge next to its title, and Coordinator 'Not yet assigned'.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The 'Awaiting assignment' table shows 'SPM30 Nusantara Developer Meetup' and 'SPM30 Meridian Graduate Evening' with their client, date and how long they have been waiting. Base-seed events that are also submitted with no coordinator (e.g. 'Nusantara Developer Summit', 'Meridian Graduate Recruitment Evening') may appear too. 'SPM30 Kirana Regional Offsite' (already has a coordinator) is not listed. 'SPM30 Draft Investor Update' (draft) is not listed. The opened event's page shows the 'Submitted' status badge next to its title, and Coordinator 'Not yet assigned'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The 'Awaiting assignment' table shows 'SPM30 Nusantara Developer Meetup' and 'SPM30 Meridian Graduate Evening' with their client, date and how long they have been waiting. Base-seed events that are also submitted with no coordinator (e.g. 'Nusantara Developer Summit', 'Meridian Graduate Recruitment Evening') may appear too. 'SPM30 Kirana Regional Offsite' (already has a coordinator) is not listed. 'SPM30 Draft Investor Update' (draft) is not listed. The opened event's page shows the 'Submitted' status badge next to its title, and Coordinator 'Not yet assigned'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC02
v2 (2026-10-20): The Event Operations Manager is now shown as the 'Event Coordinator Lead' (SPM-84 AC1, forum #129, Week 7 Change #5) - the same role, accounts, permissions and pages. Read 'Operations Manager', 'Event Operations Manager' or 'Ops Manager' in this case as 'Event Coordinator Lead'; on screen the role is shown under its new name, and refusals say 'Assigning coordinators is the Event Coordinator Lead's role.'
Item
Test Case ID | SPM-30-TC02
Pre-conditions | Test data freshly loaded: run `npm run fixtures:spm30` from the project folder just before this case. Logged in as Nadia Rahman (nadia.rahman@connectsphere.com / password123), Event Operations Manager.
Test Steps | 1. Open the Dashboard
Test Data | Expected: SPM30 Nusantara Developer Meetup, SPM30 Meridian Graduate Evening
Expected Result | The 'Awaiting assignment' section ('Submitted events with no coordinator yet.') lists 'SPM30 Nusantara Developer Meetup' and 'SPM30 Meridian Graduate Evening'. 'SPM30 Kirana Regional Offsite' is not listed.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The 'Awaiting assignment' section ('Submitted events with no coordinator yet.') lists 'SPM30 Nusantara Developer Meetup' and 'SPM30 Meridian Graduate Evening'. 'SPM30 Kirana Regional Offsite' is not listed.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The 'Awaiting assignment' section ('Submitted events with no coordinator yet.') lists 'SPM30 Nusantara Developer Meetup' and 'SPM30 Meridian Graduate Evening'. 'SPM30 Kirana Regional Offsite' is not listed.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC03
v2 (2026-10-20): The Event Operations Manager is now shown as the 'Event Coordinator Lead' (SPM-84 AC1, forum #129, Week 7 Change #5) - the same role, accounts, permissions and pages. Read 'Operations Manager', 'Event Operations Manager' or 'Ops Manager' in this case as 'Event Coordinator Lead'; on screen the role is shown under its new name, and refusals say 'Assigning coordinators is the Event Coordinator Lead's role.'
Item
Test Case ID | SPM-30-TC03
Pre-conditions | Logged out. Accounts: Daniel Tan (daniel.tan@connectsphere.com / password123), Event Coordinator; Budi Santoso (budi.santoso@nusantaratec.com / password123), Event Organiser; Marcus Wong (marcus.wong@connectsphere.com / password123), Venue Staff.
Test Steps | 1. Log in as Daniel Tan (daniel.tan@connectsphere.com / password123) 2. Check the sidebar for an 'Assignments' link 3. Type the Assignments page address /assignments into the browser address bar and press Enter 4. Log out and log in as Budi Santoso (budi.santoso@nusantaratec.com / password123) 5. Repeat the sidebar check and the direct address check 6. Log out and log in as Marcus Wong (marcus.wong@connectsphere.com / password123) 7. Repeat the sidebar check and the direct address check
Test Data | Event Coordinator: daniel.tan@connectsphere.com / password123 ¦ Event Organiser: budi.santoso@nusantaratec.com / password123 ¦ Venue Staff: marcus.wong@connectsphere.com / password123
Expected Result | For each of the three users: No 'Assignments' link is shown in the sidebar. Opening the page directly shows an access-denied message: 'Assigning coordinators is the Event Operations Manager's role.' No events or 'Assign to' controls are shown.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | For each of the three users: No 'Assignments' link is shown in the sidebar. Opening the page directly shows an access-denied message: 'Assigning coordinators is the Event Operations Manager's role.' No events or 'Assign to' controls are shown.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | For each of the three users: No 'Assignments' link is shown in the sidebar. Opening the page directly shows an access-denied message: 'Assigning coordinators is the Event Operations Manager's role.' No events or 'Assign to' controls are shown.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC04
v2 (2026-10-20): The Event Operations Manager is now shown as the 'Event Coordinator Lead' (SPM-84 AC1, forum #129, Week 7 Change #5) - the same role, accounts, permissions and pages. Read 'Operations Manager', 'Event Operations Manager' or 'Ops Manager' in this case as 'Event Coordinator Lead'; on screen the role is shown under its new name, and refusals say 'Assigning coordinators is the Event Coordinator Lead's role.'
Item
Test Case ID | SPM-30-TC04
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. Logged in as Grace Lim (grace.lim@connectsphere.com / password123).
Test Steps | 1. Click 'Assignments' in the sidebar 2. Open the 'Assign to' dropdown on the 'SPM30 Meridian Graduate Evening' row
Test Data | Expected options: Daniel Tan, Priya Raj, Joel Fernandez, Hui Shan Neo, Arif Mansor
Expected Result | The dropdown lists exactly the five Event Coordinators. No Ops Managers (Grace Lim, Nadia Rahman), Venue Staff (e.g. Marcus Wong), Technical Support (e.g. Kenji Sato), Organisers or Attendees appear.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The dropdown lists exactly the five Event Coordinators. No Ops Managers (Grace Lim, Nadia Rahman), Venue Staff (e.g. Marcus Wong), Technical Support (e.g. Kenji Sato), Organisers or Attendees appear.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The dropdown lists exactly the five Event Coordinators. No Ops Managers (Grace Lim, Nadia Rahman), Venue Staff (e.g. Marcus Wong), Technical Support (e.g. Kenji Sato), Organisers or Attendees appear.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC05
Item
Test Case ID | SPM-30-TC05
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. 'SPM30 Meridian Graduate Evening' is Submitted with no coordinator. Logged in as Grace Lim (grace.lim@connectsphere.com / password123).
Test Steps | 1. Click 'Assignments' in the sidebar 2. Leave the 'Assign to' dropdown for 'SPM30 Meridian Graduate Evening' on 'Choose a coordinator' 3. Try to click 'Assign'
Test Data | Coordinator: (none selected)
Expected Result | The 'Assign' button stays disabled while 'Choose a coordinator' is selected. The event stays in the 'Awaiting assignment' list with status Submitted.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The 'Assign' button stays disabled while 'Choose a coordinator' is selected. The event stays in the 'Awaiting assignment' list with status Submitted.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The 'Assign' button stays disabled while 'Choose a coordinator' is selected. The event stays in the 'Awaiting assignment' list with status Submitted.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC06
Item
Test Case ID | SPM-30-TC06
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. 'SPM30 Meridian Graduate Evening' is Submitted with no coordinator. Logged in as James Koh (james.koh@meridianfina.com / password123), the event's organiser.
Test Steps | 1. Click 'My Events' in the sidebar 2. Open 'SPM30 Meridian Graduate Evening'
Test Data | Event: SPM30 Meridian Graduate Evening
Expected Result | The 'Details' card shows Coordinator 'Not yet assigned'.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The 'Details' card shows Coordinator 'Not yet assigned'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The 'Details' card shows Coordinator 'Not yet assigned'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC07
Item
Test Case ID | SPM-30-TC07
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. 'SPM30 Meridian Graduate Evening' is Submitted with no coordinator. Logged in as Daniel Tan (daniel.tan@connectsphere.com / password123), Event Coordinator.
Test Steps | 1. Open the Dashboard 2. Click 'All Events' 3. Open 'SPM30 Meridian Graduate Evening' 4. Open the 'Equipment' tab
Test Data | Event: SPM30 Meridian Graduate Evening (unassigned) ¦ Viewer: Daniel Tan
Expected Result | The event does not appear under 'Awaiting your review' on Daniel Tan's dashboard. The event details can be viewed and show Coordinator 'Not yet assigned'. The Equipment tab shows 'Only the coordinator assigned to this event can view and manage its equipment requirements.' and no options to add or edit equipment.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The event does not appear under 'Awaiting your review' on Daniel Tan's dashboard. The event details can be viewed and show Coordinator 'Not yet assigned'. The Equipment tab shows 'Only the coordinator assigned to this event can view and manage its equipment requirements.' and no options to add or edit equipment.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The event does not appear under 'Awaiting your review' on Daniel Tan's dashboard. The event details can be viewed and show Coordinator 'Not yet assigned'. The Equipment tab shows 'Only the coordinator assigned to this event can view and manage its equipment requirements.' and no options to add or edit equipment.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC08
Item
Test Case ID | SPM-30-TC08
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. 'SPM30 Nusantara Developer Meetup' (organiser Budi Santoso, Nusantara Tech Labs) is Submitted with no coordinator. Logged in as Grace Lim (grace.lim@connectsphere.com / password123). Data reset: Changes data (assigns the event). TC09 and TC10 continue from this result, so reset only after TC10: run `npm run fixtures:spm30` from the project folder.
Test Steps | 1. Click 'Assignments' in the sidebar 2. In the 'Assign to' dropdown for 'SPM30 Nusantara Developer Meetup', choose 'Daniel Tan' 3. Click 'Assign' 4. Click 'All Events' and open 'SPM30 Nusantara Developer Meetup' 5. Reload the page
Test Data | Event: SPM30 Nusantara Developer Meetup ¦ Coordinator: Daniel Tan
Expected Result | The message 'Daniel Tan is now the coordinator for "SPM30 Nusantara Developer Meetup". It has moved to Under review.' is shown. 'SPM30 Nusantara Developer Meetup' disappears from the 'Awaiting assignment' list. After reloading the event page, the status badge shows 'Under review' (previously 'Submitted') and the 'Details' card shows Coordinator 'Daniel Tan'.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The message 'Daniel Tan is now the coordinator for "SPM30 Nusantara Developer Meetup". It has moved to Under review.' is shown. 'SPM30 Nusantara Developer Meetup' disappears from the 'Awaiting assignment' list. After reloading the event page, the status badge shows 'Under review' (previously 'Submitted') and the 'Details' card shows Coordinator 'Daniel Tan'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The message 'Daniel Tan is now the coordinator for "SPM30 Nusantara Developer Meetup". It has moved to Under review.' is shown. 'SPM30 Nusantara Developer Meetup' disappears from the 'Awaiting assignment' list. After reloading the event page, the status badge shows 'Under review' (previously 'Submitted') and the 'Details' card shows Coordinator 'Daniel Tan'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC09
Item
Test Case ID | SPM-30-TC09
Pre-conditions | TC08 completed: Daniel Tan is assigned to 'SPM30 Nusantara Developer Meetup'. Logged in as Daniel Tan (daniel.tan@connectsphere.com / password123). Data reset: Changes data (adds an equipment requirement). Reset after TC10: run `npm run fixtures:spm30` from the project folder.
Test Steps | 1. Open the Dashboard 2. Open 'SPM30 Nusantara Developer Meetup' from the 'Awaiting your review' list 3. Open the 'Equipment' tab 4. Add an equipment requirement and save
Test Data | Event: SPM30 Nusantara Developer Meetup ¦ Equipment: Projector x 2
Expected Result | 'SPM30 Nusantara Developer Meetup' appears under 'Awaiting your review' on Daniel Tan's dashboard. The equipment requirement is saved and shown in the list (management actions are available, not read-only).
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | 'SPM30 Nusantara Developer Meetup' appears under 'Awaiting your review' on Daniel Tan's dashboard. The equipment requirement is saved and shown in the list (management actions are available, not read-only).
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | 'SPM30 Nusantara Developer Meetup' appears under 'Awaiting your review' on Daniel Tan's dashboard. The equipment requirement is saved and shown in the list (management actions are available, not read-only).
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC10
Item
Test Case ID | SPM-30-TC10
Pre-conditions | TC08 completed: Daniel Tan is assigned to 'SPM30 Nusantara Developer Meetup'. Logged in as Budi Santoso (budi.santoso@nusantaratec.com / password123), the event's organiser. Data reset: After this case, reset the data TC08 and TC09 changed: run `npm run fixtures:spm30` from the project folder.
Test Steps | 1. Click 'My Events' in the sidebar 2. Open 'SPM30 Nusantara Developer Meetup'
Test Data | Event: SPM30 Nusantara Developer Meetup ¦ Organiser: Budi Santoso
Expected Result | The 'Details' card shows Coordinator 'Daniel Tan'.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The 'Details' card shows Coordinator 'Daniel Tan'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The 'Details' card shows Coordinator 'Daniel Tan'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC11
Item
Test Case ID | SPM-30-TC11
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. 'SPM30 Meridian Client Forum' (owned by James Koh, Meridian Financial Group) is Confirmed with coordinator Daniel Tan. Logged in as Rachel Ng (rachel.ng@meridianfina.com / password123), another organiser at Meridian Financial Group.
Test Steps | 1. Click 'My Events' in the sidebar 2. Open 'SPM30 Meridian Client Forum'
Test Data | Event: SPM30 Meridian Client Forum ¦ Viewer: Rachel Ng (same company, not owner)
Expected Result | The 'Details' card shows Coordinator 'Daniel Tan'.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The 'Details' card shows Coordinator 'Daniel Tan'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The 'Details' card shows Coordinator 'Daniel Tan'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC12
Item
Test Case ID | SPM-30-TC12
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. 'SPM30 Meridian Client Forum' is Confirmed, registration enabled, coordinator Daniel Tan. Logged in as an Attendee (lee.wei.ming@example.com / password123).
Test Steps | 1. Open 'SPM30 Meridian Client Forum' from the browse events page
Test Data | Event: SPM30 Meridian Client Forum ¦ Viewer role: Attendee
Expected Result | The event page shows its public details only. No 'Coordinator' row is shown, and the name 'Daniel Tan' does not appear anywhere on the page.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The event page shows its public details only. No 'Coordinator' row is shown, and the name 'Daniel Tan' does not appear anywhere on the page.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The event page shows its public details only. No 'Coordinator' row is shown, and the name 'Daniel Tan' does not appear anywhere on the page.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC13
Item
Test Case ID | SPM-30-TC13
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. 'SPM30 Kirana Regional Offsite' (organiser Faridah Aziz) is Under review with coordinator Priya Raj. Logged in as Grace Lim (grace.lim@connectsphere.com / password123). Data reset: Changes data (reassigns the event). TC14 continues from this result, so reset only after TC14: run `npm run fixtures:spm30` from the project folder.
Test Steps | 1. Click 'All Events' 2. Open 'SPM30 Kirana Regional Offsite' 3. In the 'Change coordinator' card, choose 'Joel Fernandez' from the dropdown 4. Click 'Reassign' 5. Click 'Reassign' in the 'Reassign this event?' confirmation 6. Reload the page
Test Data | Event: SPM30 Kirana Regional Offsite ¦ From: Priya Raj ¦ To: Joel Fernandez
Expected Result | The confirmation says the event moves from Priya Raj to Joel Fernandez. The message 'Reassigned from Priya Raj to Joel Fernandez.' is shown. After reloading, the 'Details' card shows Coordinator 'Joel Fernandez'. The event status is unchanged (Under review).
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The confirmation says the event moves from Priya Raj to Joel Fernandez. The message 'Reassigned from Priya Raj to Joel Fernandez.' is shown. After reloading, the 'Details' card shows Coordinator 'Joel Fernandez'. The event status is unchanged (Under review).
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The confirmation says the event moves from Priya Raj to Joel Fernandez. The message 'Reassigned from Priya Raj to Joel Fernandez.' is shown. After reloading, the 'Details' card shows Coordinator 'Joel Fernandez'. The event status is unchanged (Under review).
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC14
Item
Test Case ID | SPM-30-TC14
Pre-conditions | TC13 completed: 'SPM30 Kirana Regional Offsite' reassigned from Priya Raj to Joel Fernandez. Data reset: After this case, reset the data TC13 changed: run `npm run fixtures:spm30` from the project folder.
Test Steps | 1. Log in as Priya Raj (priya.raj@connectsphere.com / password123) 2. Open the Dashboard 3. Open 'SPM30 Kirana Regional Offsite' from 'All Events' and open the 'Equipment' tab 4. Log out and log in as Joel Fernandez (joel.fernandez@connectsphere.com / password123) 5. Open the Dashboard
Test Data | Event: SPM30 Kirana Regional Offsite ¦ Previous: Priya Raj ¦ New: Joel Fernandez
Expected Result | The event is no longer listed on Priya Raj's dashboard, and she sees no add/edit options on its Equipment tab. The event is listed under 'Awaiting your review' on Joel Fernandez's dashboard.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The event is no longer listed on Priya Raj's dashboard, and she sees no add/edit options on its Equipment tab. The event is listed under 'Awaiting your review' on Joel Fernandez's dashboard.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The event is no longer listed on Priya Raj's dashboard, and she sees no add/edit options on its Equipment tab. The event is listed under 'Awaiting your review' on Joel Fernandez's dashboard.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC15
v2 (2026-10-20): The Event Operations Manager is now shown as the 'Event Coordinator Lead' (SPM-84 AC1, forum #129, Week 7 Change #5) - the same role, accounts, permissions and pages. Read 'Operations Manager', 'Event Operations Manager' or 'Ops Manager' in this case as 'Event Coordinator Lead'; on screen the role is shown under its new name, and refusals say 'Assigning coordinators is the Event Coordinator Lead's role.' On the Assignments page, SPM-30's 'Assigned' tab is now 'Active events' (SPM-84 AC5): it also lists active events with no coordinator yet, under 'Not yet assigned'.
Item
Test Case ID | SPM-30-TC15
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. 'SPM30 Nusantara Product Launch' (organiser Sari Widodo) is Under review with coordinator Daniel Tan. Logged in as Nadia Rahman (nadia.rahman@connectsphere.com / password123), Event Operations Manager. Data reset: Changes data (reassigns the event). After this case, reset it: run `npm run fixtures:spm30` from the project folder.
Test Steps | 1. Click 'Assignments' in the sidebar 2. Click the 'Assigned' tab 3. Find the row for 'SPM30 Nusantara Product Launch' 4. In that row's dropdown, choose 'Hui Shan Neo' 5. Click 'Reassign' in that row 6. Click 'Reassign' in the 'Reassign this event?' confirmation 7. Click 'All Events' and open 'SPM30 Nusantara Product Launch'
Test Data | Event: SPM30 Nusantara Product Launch ¦ From: Daniel Tan ¦ To: Hui Shan Neo
Expected Result | The message '"SPM30 Nusantara Product Launch" has been reassigned from Daniel Tan to Hui Shan Neo.' is shown. The event page shows Coordinator 'Hui Shan Neo'. The event status is unchanged (Under review).
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The message '"SPM30 Nusantara Product Launch" has been reassigned from Daniel Tan to Hui Shan Neo.' is shown. The event page shows Coordinator 'Hui Shan Neo'. The event status is unchanged (Under review).
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The message '"SPM30 Nusantara Product Launch" has been reassigned from Daniel Tan to Hui Shan Neo.' is shown. The event page shows Coordinator 'Hui Shan Neo'. The event status is unchanged (Under review).
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC16
Item
Test Case ID | SPM-30-TC16
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. 'SPM30 Anchorpoint Partner Briefing' is Confirmed with coordinator Joel Fernandez; 'SPM30 Civic Trust Workshop' is Postponed with coordinator Arif Mansor. Logged in as Grace Lim (grace.lim@connectsphere.com / password123). Data reset: Changes data (reassigns both events). After this case, reset them: run `npm run fixtures:spm30` from the project folder.
Test Steps | 1. Click 'All Events' 2. Open 'SPM30 Anchorpoint Partner Briefing' 3. In the 'Change coordinator' card, choose 'Arif Mansor', click 'Reassign', then 'Reassign' in the confirmation 4. Click 'All Events' and open 'SPM30 Civic Trust Workshop' 5. In the 'Change coordinator' card, choose 'Hui Shan Neo', click 'Reassign', then 'Reassign' in the confirmation
Test Data | SPM30 Anchorpoint Partner Briefing (Confirmed): Joel Fernandez -> Arif Mansor ¦ SPM30 Civic Trust Workshop (Postponed): Arif Mansor -> Hui Shan Neo
Expected Result | Both reassignments succeed. 'SPM30 Anchorpoint Partner Briefing' shows Coordinator 'Arif Mansor' and stays 'Confirmed'. 'SPM30 Civic Trust Workshop' shows Coordinator 'Hui Shan Neo' and stays 'Postponed'.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | Both reassignments succeed. 'SPM30 Anchorpoint Partner Briefing' shows Coordinator 'Arif Mansor' and stays 'Confirmed'. 'SPM30 Civic Trust Workshop' shows Coordinator 'Hui Shan Neo' and stays 'Postponed'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | Both reassignments succeed. 'SPM30 Anchorpoint Partner Briefing' shows Coordinator 'Arif Mansor' and stays 'Confirmed'. 'SPM30 Civic Trust Workshop' shows Coordinator 'Hui Shan Neo' and stays 'Postponed'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC17
v2 (2026-10-20): On the Assignments page, SPM-30's 'Assigned' tab is now 'Active events' (SPM-84 AC5): it also lists active events with no coordinator yet, under 'Not yet assigned'.
Item
Test Case ID | SPM-30-TC17
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. 'SPM30 Harbourline Claims Training' is Completed (Priya Raj), 'SPM30 Pearl Delta Supplier Forum' is Cancelled (Joel Fernandez), 'SPM30 Selaras Overnight Field Day' is Rejected (Priya Raj). Logged in as Grace Lim (grace.lim@connectsphere.com / password123).
Test Steps | 1. Click 'All Events' 2. Open 'SPM30 Harbourline Claims Training' and look for a 'Change coordinator' card 3. Open 'SPM30 Pearl Delta Supplier Forum' and look for a 'Change coordinator' card 4. Open 'SPM30 Selaras Overnight Field Day' and look for a 'Change coordinator' card 5. Click 'Assignments', open the 'Assigned' tab, and check whether any of these three events are listed
Test Data | Events: SPM30 Harbourline Claims Training (Completed), SPM30 Pearl Delta Supplier Forum (Cancelled), SPM30 Selaras Overnight Field Day (Rejected)
Expected Result | None of the three events shows a 'Change coordinator' card. None of them appear on either Assignments tab. Each still shows its original coordinator.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | None of the three events shows a 'Change coordinator' card. None of them appear on either Assignments tab. Each still shows its original coordinator.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | None of the three events shows a 'Change coordinator' card. None of them appear on either Assignments tab. Each still shows its original coordinator.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC18
Item
Test Case ID | SPM-30-TC18
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. 'SPM30 Straits Journal Club' is Under review with coordinator Joel Fernandez. Logged in as Grace Lim (grace.lim@connectsphere.com / password123).
Test Steps | 1. Click 'All Events' 2. Open 'SPM30 Straits Journal Club' 3. In the 'Change coordinator' card, choose 'Joel Fernandez' (the current coordinator) from the dropdown
Test Data | Event: SPM30 Straits Journal Club ¦ Coordinator: Joel Fernandez -> Joel Fernandez
Expected Result | The message 'Joel Fernandez is already the assigned coordinator.' appears under the dropdown. The 'Reassign' button stays disabled. The coordinator remains 'Joel Fernandez'.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | The message 'Joel Fernandez is already the assigned coordinator.' appears under the dropdown. The 'Reassign' button stays disabled. The coordinator remains 'Joel Fernandez'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | The message 'Joel Fernandez is already the assigned coordinator.' appears under the dropdown. The 'Reassign' button stays disabled. The coordinator remains 'Joel Fernandez'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC19
Item
Test Case ID | SPM-30-TC19
Pre-conditions | Test data loaded: run `npm run fixtures:spm30` from the project folder if it has not been run for this test pass. 'SPM30 Straits Journal Club' is Under review with coordinator Joel Fernandez (organiser Raj Kumar).
Test Steps | 1. Log in as Joel Fernandez (joel.fernandez@connectsphere.com / password123) 2. Click 'All Events', open 'SPM30 Straits Journal Club' and look for a 'Change coordinator' card 3. Log out and log in as Raj Kumar (raj.kumar@straitsmedic.com / password123) 4. Click 'My Events', open 'SPM30 Straits Journal Club' and look for a 'Change coordinator' card
Test Data | Event: SPM30 Straits Journal Club ¦ Roles: Event Coordinator, Event Organiser
Expected Result | Neither user sees a 'Change coordinator' card or any other way to assign or change the coordinator. The 'Details' card shows Coordinator 'Joel Fernandez' as read-only text.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | Neither user sees a 'Change coordinator' card or any other way to assign or change the coordinator. The 'Details' card shows Coordinator 'Joel Fernandez' as read-only text.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | Neither user sees a 'Change coordinator' card or any other way to assign or change the coordinator. The 'Details' card shows Coordinator 'Joel Fernandez' as read-only text.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30

## TC20
Item
Test Case ID | SPM-30-TC20
Pre-conditions | Test data freshly loaded: run `npm run fixtures:spm30` from the project folder just before this case. Run this case last in the pass: it assigns every event waiting for a coordinator, including two base-seed events other stories' test cases rely on. Logged in as Grace Lim (grace.lim@connectsphere.com / password123). Data reset: after this case, run `npm run fixtures:spm30 -- --restore-queue` from the project folder.
Test Steps | 1. Click 'Assignments' in the sidebar 2. Check the 'Awaiting assignment' list contains only the four expected events (see test data); if it lists any other event, stop and do not assign it 3. For each event in the list, choose 'Daniel Tan' in its 'Assign to' dropdown and click 'Assign' 4. Reload the page
Test Data | Expected queue before assigning (4 events): SPM30 Nusantara Developer Meetup, SPM30 Meridian Graduate Evening, Nusantara Developer Summit, Meridian Graduate Recruitment Evening ¦ Coordinator for all: Daniel Tan
Expected Result | After the last assignment, and again after reloading, the 'Awaiting assignment' tab shows the message 'No events are awaiting assignment' with 'Every submitted event has a coordinator.' No table rows and no error are shown.
Created By | Kristen
Creation Date | 2026-09-28
Item
Actual Result | After the last assignment, and again after reloading, the 'Awaiting assignment' tab shows the message 'No events are awaiting assignment' with 'Every submitted event has a coordinator.' No table rows and no error are shown.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kristen
Date of Execution | 2026-09-29
Item
Actual Result | After the last assignment, and again after reloading, the 'Awaiting assignment' tab shows the message 'No events are awaiting assignment' with 'Every submitted event has a coordinator.' No table rows and no error are shown.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-09-30