## Summary
Story | SPM-42: As an Event Coordinator, I want to submit a venue booking request for an event so that Venue Staff can review whether the venue can be made available
Sheet | Test Case ID | Title | Linked AC | Type | Source | Status | Superseded by | Change #
TC01 | SPM-42-TC01 | Coordinator requests a suitable venue, with venue requirements and layout | AC1, AC6 | Positive | Acceptance Criteria | Updated |  | #128 (Week 7 #1)
TC02 | SPM-42-TC02 | Coordinator cannot request an unsuitable venue, and sees why | AC1 | Negative | Acceptance Criteria | Active
RETIRED – TC03 | SPM-42-TC03 | A request for one slot books that whole slot; venue requirements may be left empty | AC2, AC6 | Positive | Acceptance Criteria | Retired | SPM-93-TC01 | #128 (Week 7 #1)
RETIRED – TC04 | SPM-42-TC04 | An event with no sessions spanning AM and PM is requested on its own date and consumes both slots in full | AC2, AC4 | Positive | Acceptance Criteria | Retired | SPM-42-TC04-R (Sprint-3 regression); SPM-93-TC01 | #128 (Week 7 #1)
RETIRED – TC05 | SPM-42-TC05 | Slot choices that are empty, or not next to each other, are refused (team decision: contiguous slots) | AC2 | Negative | Code | Retired | SPM-93-TC03 | #128 (Week 7 #1)
RETIRED – TC06 | SPM-42-TC06 | Setup and turnaround each take exactly one adjacent slot, including the previous or following day | AC3, AC2 | Boundary | Acceptance Criteria | Retired | SPM-93-TC01 | #128 (Week 7 #1)
RETIRED – TC07 | SPM-42-TC07 | A venue with no setup or turnaround holds only the chosen slots, even one more than the event needs | AC3, AC2 | Boundary | Acceptance Criteria | Retired | SPM-93-TC08 | #128 (Week 7 #1)
RETIRED – TC08 | SPM-42-TC08 | Slots that do not cover the session's (or event's) own time are refused | AC4, AC2 | Negative | Acceptance Criteria | Retired | SPM-93-TC04 | #128 (Week 7 #1)
TC09 | SPM-42-TC09 | A 3-session event gets one request per session, each using its session's date, time and layout | AC4, AC5 | Positive | Acceptance Criteria | Updated |  | #128 (Week 7 #1)
TC10 | SPM-42-TC10 | Venue Staff see which event, and which session, each request belongs to | AC5 | Positive | Acceptance Criteria | Active
TC11 | SPM-42-TC11 | The request reaches Venue Staff and shows Pending | AC7, AC8 | Positive | Acceptance Criteria | Updated |  | #128 (Week 7 #1)
TC12 | SPM-42-TC12 | Only the event's assigned Coordinator can request a booking (SPM-30 assignment rule) | AC7, AC1 | Negative | Code | Updated |  | Week 7 #5
TC13 | SPM-42-TC13 | A venue cannot be requested for a completed, cancelled or rejected event (existing SPM-47 rule) | AC7 | Negative | Code | Updated |  | #103
TC14 | SPM-42-TC14 | A slot that is booked, on hold, or unavailable is refused (#35, #41) | AC2 | Negative | Code | Updated |  | #128 (Week 7 #1)
RETIRED – TC15 | SPM-42-TC15 | A clash only through setup or turnaround slots is refused (#123, #35) | AC2, AC3 | Boundary | Code | Retired | SPM-93-TC09 | #128 (Week 7 #1)
TC16 | SPM-42-TC16 | Cancelled and rejected bookings do not block a request (#41) | AC2, AC3 | Boundary | Code | Updated |  | #128 (Week 7 #1)
AC | Acceptance Criterion |  |  | Covered by
AC1 | The Event Coordinator can select a suitable venue. |  |  | SPM-42-TC01 SPM-42-TC02 SPM-42-TC12
AC2 | The request specifies one or more of the venue's fixed AM, PM or Night slots for the required date; an event spanning multiple slots consumes each of them in full. |  |  | SPM-42-TC03 SPM-42-TC04 SPM-42-TC05 SPM-42-TC06 SPM-42-TC07 SPM-42-TC08 SPM-42-TC14 SPM-42-TC15 SPM-42-TC16
AC3 | Where setup or turnaround time is required, the immediately adjacent slot (before the event for setup, after for turnaround, including the previous or following day where applicable) is included in the request. |  |  | SPM-42-TC06 SPM-42-TC07 SPM-42-TC15 SPM-42-TC16
AC4 | For a multi-session event, a booking request is made per session, using that session's own date, time and requirements rather than the event's. |  |  | SPM-42-TC04 SPM-42-TC08 SPM-42-TC09
AC5 | The request is associated with the relevant event (and session, where applicable). |  |  | SPM-42-TC09 SPM-42-TC10
AC6 | Venue requirements are included in the request. |  |  | SPM-42-TC01 SPM-42-TC03
AC7 | The request is submitted to Venue Staff for review. |  |  | SPM-42-TC11 SPM-42-TC12 SPM-42-TC13
AC8 | The venue booking request has a pending status. |  |  | SPM-42-TC11
Code reviewed | src/lib/venueBookingRequest.ts src/lib/__tests__/venueBookingRequest.test.ts src/lib/venueSlots.ts src/lib/venueSuitability.ts src/lib/venueSearch.ts src/lib/permissions.ts src/lib/__tests__/permissions.test.ts src/app/events/[id]/venue/page.tsx prisma/schema.prisma prisma/seed.ts scripts/seed-spm30.ts docs/CUSTOMER_CLARIFICATIONS.md

## TC01
v2 (2026-10-19): Venue bookings are now made for a start and end time on a 15-minute grid (SPM-93, discussion #128, Week 7 Change #1). Read every AM / PM / Night slot in this case as the event's (or session's) own start and end times; setup and turnaround are the venue's minutes either side, not whole slots, and the calendar has one Schedule column instead of slot columns. The behaviour this case checks is unchanged. A rewritten version, SPM-42-TC01-R, was run on 2026-10-17/18 in docs/regression/Sprint-3_Regression.xlsx.
Item
Test Case ID | SPM-42-TC01
Pre-conditions | npm run fixtures:spm42 has been run once at the start of this test pass (do not re-run it between cases - later cases use requests made in earlier ones). Logged in as Coordinator Daniel Tan (daniel.tan@connectsphere.com / password123), assigned to spm42_symposium 'SPM42 Research Symposium' (status Planning, 4 Mar 2027 (2026-09-26 + 159) 09:00-18:00, expects 200, layout Theatre, no sessions). Changi Conference Centre (CBP-CONF) has Theatre capacity 260.
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'SPM42 Research Symposium' in the list 4. Click the 'Venue' tab 5. Find 'Changi Conference Centre (CBP-CONF)' in the venue list and check the badge next to it 6. Click 'Request booking' on Changi Conference Centre 7. Check the Date shows 4 Mar 2027 and only 'AM (07:00–12:00)' and 'PM (13:00–18:00)' are ticked 8. Click in the 'Venue requirements' box and type: Lectern and stage riser at the front; two wireless microphones; doors open 08:30. 9. Click 'Submit request' 10. Log out, then log in as marcus.wong@connectsphere.com / password123 11. Click 'Booking Requests' in the sidebar 12. Find the row for SPM42 Research Symposium and read its Layout and Requirements
Test Data | Event: SPM42 Research Symposium Venue: Changi Conference Centre (CBP-CONF) Date: 4 Mar 2027 (2026-09-26 + 159) Slots: AM, PM Venue requirements: Lectern and stage riser at the front; two wireless microphones; doors open 08:30.
Expected Result | Changi Conference Centre is shown as Suitable. The booking request screen opens for 'SPM42 Research Symposium' at 'Changi Conference Centre (CBP-CONF)'. After submitting, 'Booking request sent to Venue Staff.' is shown. Marcus Wong sees the request with Layout 'Theatre' and the requirements exactly as typed.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | Changi Conference Centre is shown as Suitable. The booking request screen opens for 'SPM42 Research Symposium' at 'Changi Conference Centre (CBP-CONF)'. After submitting, 'Booking request sent to Venue Staff.' is shown. Marcus Wong sees the request with Layout 'Theatre' and the requirements exactly as typed.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | Changi Conference Centre showed the status chip 'Suitable' with no blocking reasons and a Request booking button. The booking screen opened for the event at that venue; after entering 'Theatre layout, lectern and roving mic.' and submitting, 'Booking request sent to Venue Staff.' was shown. On Marcus Wong's Booking Requests screen the row reads: 'SPM42 Research Symposium ¦ Changi Conference Centre (CBP-CONF) ¦ 4 Mar 2027 · AM, PM (07:00-18:00) ¦ Layout: Theatre ¦ Theatre layout, lectern and roving mic. ¦ Daniel Tan ¦ Pending'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## TC02
Item
Test Case ID | SPM-42-TC02
Pre-conditions | npm run fixtures:spm42 has been run once at the start of this test pass (do not re-run it between cases - later cases use requests made in earlier ones). Logged in as Daniel Tan, assigned to 'SPM42 Research Symposium' (expects 200, Theatre). One-North Auditorium (ONE-AUD) has Theatre capacity 180.
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'SPM42 Research Symposium' in the list 4. Click the 'Venue' tab 5. Find 'One-North Auditorium (ONE-AUD)' in the venue list 6. Read the badge and the reason shown under it 7. Look for a 'Request booking' button on it
Test Data | Venue: One-North Auditorium, Theatre capacity 180 Expected attendance: 200
Expected Result | One-North Auditorium is shown greyed as not suitable with the reason 'Theatre capacity is 180 - your event expects 200.' It has no 'Request booking' button.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | One-North Auditorium is shown greyed as not suitable with the reason 'Theatre capacity is 180 - your event expects 200.' It has no 'Request booking' button.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | One-North Auditorium showed the chip 'Not suitable' with the single reason 'Theatre capacity is 180 - your event expects 200.' Its card carried no Request booking button at all.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## TC09
v2 (2026-10-19): Venue bookings are now made for a start and end time on a 15-minute grid (SPM-93, discussion #128, Week 7 Change #1). Read every AM / PM / Night slot in this case as the event's (or session's) own start and end times; setup and turnaround are the venue's minutes either side, not whole slots, and the calendar has one Schedule column instead of slot columns. The behaviour this case checks is unchanged. A rewritten version, SPM-42-TC09-R, was run on 2026-10-17/18 in docs/regression/Sprint-3_Regression.xlsx.
Item
Test Case ID | SPM-42-TC09
Pre-conditions | npm run fixtures:spm42 has been run once at the start of this test pass (do not re-run it between cases - later cases use requests made in earlier ones). Logged in as Daniel Tan, assigned to spm42_three_sessions 'SPM42 Three-Session Forum' (status Approved). Sessions: 'Day 1' 1 Mar 2027 (2026-09-26 + 156) 09:00-12:00, expects 80, Theatre; 'Day 2' 2 Mar 2027 (2026-09-26 + 157) 14:00-17:00, expects 30, Classroom; 'Day 3' 3 Mar 2027 (2026-09-26 + 158) 19:00-22:00, expects 60, Banquet.
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'SPM42 Three-Session Forum' in the list 4. Click the 'Venue' tab 5. In the 'Session' drop-down, choose 'Day 1' 6. Find 'Orchard Seminar Room (ORC-SEM)' in the venue list and click its 'Request booking' button 7. Check the Session, Date, ticked slot and Layout shown, then click 'Submit request' and click 'Back to Venue' 8. In the 'Session' drop-down, choose 'Day 2' 9. Find 'Orchard Studio (ORC-STU)' in the venue list and click its 'Request booking' button 10. Check the Session, Date, ticked slot and Layout shown, then click 'Submit request' and click 'Back to Venue' 11. In the 'Session' drop-down, choose 'Day 3' 12. Find 'Orchard Gallery (ORC-GAL)' in the venue list and click its 'Request booking' button 13. Check the Session, Date, ticked slot and Layout shown, then click 'Submit request' and click 'Back to Venue' 14. Read the three requests under 'Booking requests'
Test Data | Day 1: Orchard Seminar Room, 1 Mar 2027, AM Day 2: Orchard Studio, 2 Mar 2027, PM Day 3: Orchard Gallery, 3 Mar 2027, Night
Expected Result | Each screen opens on its own session's date with its slot already ticked: Day 1 → 1 Mar 2027 AM; Day 2 → 2 Mar 2027 PM; Day 3 → 3 Mar 2027 Night. Three separate requests are listed, each labelled with its session and showing that session's layout: Day 1 Theatre, Day 2 Classroom, Day 3 Banquet.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | Each screen opens on its own session's date with its slot already ticked: Day 1 → 1 Mar 2027 AM; Day 2 → 2 Mar 2027 PM; Day 3 → 3 Mar 2027 Night. Three separate requests are listed, each labelled with its session and showing that session's layout: Day 1 Theatre, Day 2 Classroom, Day 3 Banquet.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | Each session opened on its own date with its own slot already ticked - Day 1: 1 Mar 2027 AM; Day 2: 2 Mar 2027 PM; Day 3: 3 Mar 2027 Night - and each at its own venue. Three separate requests are listed, each labelled with its session and its own layout: '1 Mar 2027 · AM (07:00-12:00) · Theatre', '2 Mar 2027 · PM (13:00-18:00) · Classroom', '3 Mar 2027 · Night (19:00-24:00) · Banquet'. All three Pending.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Each session's layout differs from the others, which is what shows the request uses the session's own requirements rather than the event's.
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## TC10
Item
Test Case ID | SPM-42-TC10
Pre-conditions | TC04 and TC09 have been run. Logged in as Venue Staff Marcus Wong (marcus.wong@connectsphere.com / password123).
Test Steps | 1. Log in as marcus.wong@connectsphere.com / password123 2. Click 'Booking Requests' in the sidebar 3. Find the row for Orchard Seminar Room on 6 Mar 2027 and read its Event column 4. Find the row for Orchard Studio on 2 Mar 2027 and read its Event column 5. Click the EVT- reference in the 2 Mar row
Test Data | Requests: SPM42 Town Hall (no sessions); SPM42 Three-Session Forum, Day 2
Expected Result | The 6 Mar request shows the event reference (EVT-…) and title 'SPM42 Town Hall', with no session. The 2 Mar request shows 'SPM42 Three-Session Forum' and session 'Day 2'. Clicking an event reference opens that event.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | The 6 Mar request shows the event reference (EVT-…) and title 'SPM42 Town Hall', with no session. The 2 Mar request shows 'SPM42 Three-Session Forum' and session 'Day 2'. Clicking an event reference opens that event.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | On Marcus Wong's Booking Requests screen the Town Hall row reads 'EVT-000759 ¦ SPM42 Town Hall ¦ Orchard Seminar Room (ORC-SEM) ¦ 6 Mar 2027 · AM, PM (07:00-18:00)' with no session named. The Three-Session row reads 'EVT-000765 ¦ SPM42 Three-Session Forum ¦ Session: Day 2 ¦ Orchard Studio (ORC-STU) ¦ 2 Mar 2027 · PM (13:00-18:00)'. Event references are rendered as links to the event.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## TC11
v2 (2026-10-19): Venue bookings are now made for a start and end time on a 15-minute grid (SPM-93, discussion #128, Week 7 Change #1). Read every AM / PM / Night slot in this case as the event's (or session's) own start and end times; setup and turnaround are the venue's minutes either side, not whole slots, and the calendar has one Schedule column instead of slot columns. The behaviour this case checks is unchanged. A rewritten version, SPM-42-TC11-R, was run on 2026-10-17/18 in docs/regression/Sprint-3_Regression.xlsx.
Item
Test Case ID | SPM-42-TC11
Pre-conditions | TC04 has been run.
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'SPM42 Town Hall' in the list 4. Click the 'Venue' tab 5. Read the status badge of the request under 'Booking requests' 6. Log out, then log in as marcus.wong@connectsphere.com / password123 7. Click 'Booking Requests' in the sidebar 8. Find the row for SPM42 Town Hall and read every column
Test Data | Request: SPM42 Town Hall, Orchard Seminar Room, 6 Mar 2027, AM + PM
Expected Result | Both screens show the request with the status badge 'Pending'. Marcus Wong's row shows Orchard Seminar Room, '6 Mar 2027 · AM, PM (07:00–18:00)', 'Setup: 5 Mar 2027 Night (19:00–24:00)', 'Turnaround: 6 Mar 2027 Night (19:00–24:00)', and Requested by Daniel Tan.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | Both screens show the request with the status badge 'Pending'. Marcus Wong's row shows Orchard Seminar Room, '6 Mar 2027 · AM, PM (07:00–18:00)', 'Setup: 5 Mar 2027 Night (19:00–24:00)', 'Turnaround: 6 Mar 2027 Night (19:00–24:00)', and Requested by Daniel Tan.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | The Venue Staff row shows 'Orchard Seminar Room (ORC-SEM) ¦ 6 Mar 2027 · AM, PM (07:00-18:00) ¦ Setup: 5 Mar 2027 Night (19:00-24:00) ¦ Turnaround: 6 Mar 2027 Night (19:00-24:00) ¦ Layout: Theatre ¦ Daniel Tan ¦ Pending'. The Coordinator's own Venue tab shows the same request with the status badge Pending.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## TC12
v2 (2026-10-20): The Event Operations Manager is now shown as the 'Event Coordinator Lead' (SPM-84 AC1, forum #129, Week 7 Change #5) - the same role, accounts, permissions and pages. Read 'Operations Manager', 'Event Operations Manager' or 'Ops Manager' in this case as 'Event Coordinator Lead'; on screen the role is shown under its new name, and refusals say 'Assigning coordinators is the Event Coordinator Lead's role.'
Item
Test Case ID | SPM-42-TC12
Pre-conditions | Seeded data: 'Town Hall Q4' (status Planning) is assigned to Daniel Tan. Accounts (password123): Coordinator Priya Raj (priya.raj@connectsphere.com), Organiser Rachel Ng (rachel.ng@meridianfina.com, organiser of 'Town Hall Q4'), Ops Manager Grace Lim (grace.lim@connectsphere.com), Venue Staff Marcus Wong (marcus.wong@connectsphere.com), Technical Support Kenji Sato (kenji.sato@connectsphere.com).
Test Steps | 1. Log in as priya.raj@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'Town Hall Q4' in the list 4. Click the 'Venue' tab 5. Read the message above the venue list and look for any 'Request booking' button 6. Log out, log in as rachel.ng@meridianfina.com / password123, click 'My Events', click 'Town Hall Q4' and look for a 'Venue' tab 7. Log out, log in as grace.lim@connectsphere.com / password123, click 'All Events', click 'Town Hall Q4' and look for a 'Venue' tab 8. Log out, log in as marcus.wong@connectsphere.com / password123, click 'Booking Requests' and look for any 'Request booking' button 9. Log out, log in as kenji.sato@connectsphere.com / password123 and look through the sidebar for anywhere to request a venue
Test Data | Accounts: Priya Raj (Coordinator, not assigned), Rachel Ng (Organiser), Grace Lim (Ops Manager), Marcus Wong (Venue Staff), Kenji Sato (Technical Support)
Expected Result | None of the five sees a 'Request booking' button anywhere for this event. Priya Raj's Venue tab says 'Only the assigned Coordinator can request a venue booking.'
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | None of the five sees a 'Request booking' button anywhere for this event. Priya Raj's Venue tab says 'Only the assigned Coordinator can request a venue booking.'
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | None of the five accounts saw a Request booking button anywhere for the event. Priya Raj (a Coordinator who is not the assigned one), Grace Lim and Marcus Wong each saw 'Only the assigned Coordinator can request a venue booking.' Rachel Ng and Kenji Sato have no Venue tab for the event at all, so the question never arises for them.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The refusal is shown to roles that can open the Venue tab; the Organiser and Technical Support are stopped a step earlier by not being offered the tab. Both outcomes satisfy the criterion - no button for any of the five.
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## TC13
v2 (2026-10-23): The page now reads 'A venue cannot be requested for a completed, cancelled, rejected or withdrawn event.' instead of 'A venue cannot be requested for a completed, cancelled or rejected event.' (SPM-59, discussion #103: the messages that refuse an action on a closed event now name withdrawn events too). Read the expected result with the new wording. The behaviour this case checks is unchanged.
Item
Test Case ID | SPM-42-TC13
Pre-conditions | Seeded data. Logged in as Coordinator Joel Fernandez (joel.fernandez@connectsphere.com / password123), assigned to 'Pearl Delta Supplier Forum' (status Cancelled, 29 Oct 2026 (2026-09-26 + 33) 09:00-14:00).
Test Steps | 1. Log in as joel.fernandez@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'Pearl Delta Supplier Forum' in the list 4. Click the 'Venue' tab 5. Read the message above the venue list and look for any 'Request booking' button
Test Data | Event status: Cancelled
Expected Result | No 'Request booking' button is shown. The page says 'A venue cannot be requested for a completed, cancelled or rejected event.'
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | No 'Request booking' button is shown. The page says 'A venue cannot be requested for a completed, cancelled or rejected event.'
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | On the cancelled event's Venue tab the page read 'A venue cannot be requested for a completed, cancelled or rejected event.' and no Request booking button was present on any venue card.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## TC14
v2 (2026-10-19): Venue bookings are now made for a start and end time on a 15-minute grid (SPM-93, discussion #128, Week 7 Change #1). Read every AM / PM / Night slot in this case as the event's (or session's) own start and end times; setup and turnaround are the venue's minutes either side, not whole slots, and the calendar has one Schedule column instead of slot columns. The behaviour this case checks is unchanged.
Item
Test Case ID | SPM-42-TC14
Pre-conditions | npm run fixtures:spm42 has been run once at the start of this test pass (do not re-run it between cases - later cases use requests made in earlier ones). Seeded data, unchanged: - 'Product Showcase' has an Approved booking at Marina Auditorium (MAR-AUD), 21 Oct 2026 (2026-09-26 + 25) 11:00-15:00. - 'Pearl Delta Safety Conference' has a Pending booking at Changi Conference Centre (CBP-CONF), 14 Dec 2026 (2026-09-26 + 79) 09:00-17:00. - Marina Auditorium is unavailable for maintenance 20-21 Nov 2026 (2026-09-26 + 55 to + 56). Logged in as Daniel Tan, assigned to the three events in Test data (status Planning, no sessions, no booking).
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'SPM42 Clash Check' in the list 4. Click the 'Venue' tab 5. Find 'Marina Auditorium (MAR-AUD)' in the venue list and click its 'Request booking' button 6. Make sure 'AM (07:00–12:00)' and 'PM (13:00–18:00)' are ticked for 21 Oct 2026, click 'Submit request' and read the message 7. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 8. Click 'Staff Retreat' in the list 9. Click the 'Venue' tab 10. Find 'Changi Conference Centre (CBP-CONF)' in the venue list and click its 'Request booking' button 11. Make sure 'AM (07:00–12:00)' and 'PM (13:00–18:00)' are ticked for 14 Dec 2026, click 'Submit request' and read the message 12. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 13. Click 'Sports Meet' in the list 14. Click the 'Venue' tab 15. Find 'Marina Auditorium (MAR-AUD)' in the venue list and click its 'Request booking' button 16. Make sure 'AM (07:00–12:00)' and 'PM (13:00–18:00)' are ticked for 20 Nov 2026, click 'Submit request' and read the message
Test Data | 1. spm42_clash_check 'SPM42 Clash Check', 21 Oct 2026 11:00-15:00, Marina Auditorium (Approved booking) 2. 'Staff Retreat', 14 Dec 2026 09:00-17:00, Changi Conference Centre (Pending hold) 3. 'Sports Meet', 20 Nov 2026 09:00-17:00, Marina Auditorium (maintenance)
Expected Result | 1. 'Marina Auditorium is already booked for this time.' 2. 'Changi Conference Centre is on hold for another event at this time.' 3. 'Marina Auditorium is unavailable at this time.' No request is created for any of the three.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | 1. 'Marina Auditorium is already booked for this time.' 2. 'Changi Conference Centre is on hold for another event at this time.' 3. 'Marina Auditorium is unavailable at this time.' No request is created for any of the three.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | 1. SPM42 Clash Check at Marina Auditorium, 21 Oct 2026: 'Marina Auditorium is already booked for this time.' 2. Staff Retreat at Changi Conference Centre, 14 Dec 2026: 'Changi Conference Centre is on hold for another event at this time.' 3. Sports Meet at Marina Auditorium, 20 Nov 2026: 'Marina Auditorium is unavailable at this time.' No request was created in any of the three.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The three refusals are worded differently from each other, so a tester can tell an approved booking from a pending hold from a maintenance period without leaving the screen.
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## TC16
v2 (2026-10-19): Venue bookings are now made for a start and end time on a 15-minute grid (SPM-93, discussion #128, Week 7 Change #1). Read every AM / PM / Night slot in this case as the event's (or session's) own start and end times; setup and turnaround are the venue's minutes either side, not whole slots, and the calendar has one Schedule column instead of slot columns. The behaviour this case checks is unchanged.
Item
Test Case ID | SPM-42-TC16
Pre-conditions | npm run fixtures:spm42 has been run once at the start of this test pass (do not re-run it between cases - later cases use requests made in earlier ones). It creates: - 'SPM42 Cancelled Hold' with a Cancelled booking at Orchard Gallery (ORC-GAL), 15 Mar 2027 (2026-09-26 + 170) 09:00-17:00. - 'SPM42 Rejected Hold' with a Rejected booking at Marina Auditorium (MAR-AUD), 16 Mar 2027 (2026-09-26 + 171) 09:00-18:00 — had it been approved, its turnaround would hold 16 Mar Night. Logged in as Daniel Tan, assigned to the two events in Test data (status Planning, no sessions).
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'SPM42 After Cancellation' in the list 4. Click the 'Venue' tab 5. Find 'Orchard Gallery (ORC-GAL)' in the venue list and click its 'Request booking' button 6. Make sure 'AM (07:00–12:00)' and 'PM (13:00–18:00)' are ticked for 15 Mar 2027, click 'Submit request' and read the message 7. Click 'Back to Venue' and read the status under 'Booking requests' 8. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 9. Click 'SPM42 After Rejection' in the list 10. Click the 'Venue' tab 11. Find 'Marina Auditorium (MAR-AUD)' in the venue list and click its 'Request booking' button 12. Make sure 'AM (07:00–12:00)' and 'PM (13:00–18:00)' are ticked for 17 Mar 2027, click 'Submit request' and read the message 13. Click 'Back to Venue' and read the status under 'Booking requests'
Test Data | 1. spm42_after_cancel 'SPM42 After Cancellation', 15 Mar 2027 10:00-16:00, Orchard Gallery (same slots as the cancelled booking) 2. spm42_after_reject 'SPM42 After Rejection', 17 Mar 2027 (2026-09-26 + 172) 10:00-16:00, Marina Auditorium (its setup takes 16 Mar Night)
Expected Result | Both show 'Booking request sent to Venue Staff.' and the request is Pending.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | Both show 'Booking request sent to Venue Staff.' and the request is Pending.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | SPM42 After Cancellation at Orchard Gallery, over the same slots as the cancelled booking: 'Booking request sent to Venue Staff.', status Pending. SPM42 After Rejection at Marina Auditorium, whose setup needs the slot a rejected booking's turnaround would have held: also sent and Pending.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Neither a cancelled nor a rejected booking holds a slot (#41), including the setup and turnaround slots either side of it.
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## RETIRED – TC03
Item
Test Case ID | SPM-42-TC03
Pre-conditions | npm run fixtures:spm42 has been run once at the start of this test pass (do not re-run it between cases - later cases use requests made in earlier ones). Logged in as Daniel Tan, assigned to spm42_morning_talk 'SPM42 Morning Talk' (status Planning, 5 Mar 2027 (2026-09-26 + 160) 10:00-12:00, no sessions).
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'SPM42 Morning Talk' in the list 4. Click the 'Venue' tab 5. Find 'Orchard Seminar Room (ORC-SEM)' in the venue list and click its 'Request booking' button 6. Check the Date shows 5 Mar 2027 and only 'AM (07:00–12:00)' is ticked 7. Leave the 'Venue requirements' box empty 8. Click 'Submit request' 9. Click 'Back to Venue' and read the request under 'Booking requests' 10. Log out, then log in as marcus.wong@connectsphere.com / password123 11. Click 'Booking Requests' in the sidebar 12. Find the row for SPM42 Morning Talk and read its Requirements
Test Data | Date: 5 Mar 2027 (2026-09-26 + 160) Slots: AM Venue requirements: (empty)
Expected Result | 'Booking request sent to Venue Staff.' is shown. Under 'Booking requests' the request reads '5 Mar 2027 · AM (07:00–12:00)' — the whole slot, not the event's own 10:00–12:00. Marcus Wong's Booking Requests row shows Requirements 'None given'.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | 'Booking request sent to Venue Staff.' is shown. Under 'Booking requests' the request reads '5 Mar 2027 · AM (07:00–12:00)' — the whole slot, not the event's own 10:00–12:00. Marcus Wong's Booking Requests row shows Requirements 'None given'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | AM was already ticked when the booking screen opened. After submitting, the request listed on the Venue tab reads '5 Mar 2027 · AM (07:00-12:00) · Theatre' with status Pending - the whole slot, not the event's own 10:00-12:00. Venue Staff's row shows the requirements as 'None given'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## RETIRED – TC04
Item
Test Case ID | SPM-42-TC04
Pre-conditions | npm run fixtures:spm42 has been run once at the start of this test pass (do not re-run it between cases - later cases use requests made in earlier ones). Logged in as Daniel Tan, assigned to spm42_town_hall 'SPM42 Town Hall' (status Planning, 6 Mar 2027 (2026-09-26 + 161) 09:00-17:00, no sessions).
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'SPM42 Town Hall' in the list 4. Click the 'Venue' tab 5. Check there is no 'Session' drop-down above the venue list 6. Find 'Orchard Seminar Room (ORC-SEM)' in the venue list and click its 'Request booking' button 7. Check the Date shows 6 Mar 2027 and 'AM (07:00–12:00)' and 'PM (13:00–18:00)' are already ticked 8. Click 'Submit request' 9. Click 'Back to Venue' and read the request under 'Booking requests'
Test Data | Event: SPM42 Town Hall (no sessions) Date: 6 Mar 2027 (2026-09-26 + 161) Slots: AM, PM
Expected Result | No Session drop-down is shown. The Date is 6 Mar 2027 with AM and PM already ticked (the event's own time). 'Booking request sent to Venue Staff.' is shown. Under 'Booking requests' the request reads '6 Mar 2027 · AM, PM (07:00–18:00)'.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | No Session drop-down is shown. The Date is 6 Mar 2027 with AM and PM already ticked (the event's own time). 'Booking request sent to Venue Staff.' is shown. Under 'Booking requests' the request reads '6 Mar 2027 · AM, PM (07:00–18:00)'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | No Session drop-down was present. The booking screen opened on the event's own date with AM and PM ticked and Night clear. The request reads '6 Mar 2027 · AM, PM (07:00-18:00) · Theatre', Pending.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## RETIRED – TC05
Item
Test Case ID | SPM-42-TC05
Pre-conditions | npm run fixtures:spm42 has been run once at the start of this test pass (do not re-run it between cases - later cases use requests made in earlier ones). Logged in as Daniel Tan, assigned to spm42_refusals 'SPM42 Refusal Checks' (status Planning, 7 Mar 2027 (2026-09-26 + 162) 09:00-17:00, no sessions). Booking request screen open for it at 'Orchard Seminar Room (ORC-SEM)'.
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'SPM42 Refusal Checks' in the list 4. Click the 'Venue' tab 5. Find 'Orchard Seminar Room (ORC-SEM)' in the venue list and click its 'Request booking' button 6. Untick 'AM (07:00–12:00)' and 'PM (13:00–18:00)' so no slot is ticked 7. Click 'Submit request' and read the message 8. Tick 'AM (07:00–12:00)' and 'Night (19:00–24:00)'; leave 'PM (13:00–18:00)' unticked 9. Click 'Submit request' and read the message 10. Click 'Cancel' and check 'Booking requests' on the Venue tab
Test Data | Date: 7 Mar 2027 (2026-09-26 + 162) Attempt 1: no slots Attempt 2: AM, Night
Expected Result | Attempt 1 shows 'Choose at least one slot.' Attempt 2 shows 'Choose slots that are next to each other — AM and Night cannot be booked without PM.' No request is created for 'SPM42 Refusal Checks'.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | Attempt 1 shows 'Choose at least one slot.' Attempt 2 shows 'Choose slots that are next to each other — AM and Night cannot be booked without PM.' No request is created for 'SPM42 Refusal Checks'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | Submitting with no slot ticked showed 'Choose at least one slot.' Submitting with AM and Night ticked showed 'Choose slots that are next to each other - AM and Night cannot be booked without PM.' No request was created for the event.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## RETIRED – TC06
Item
Test Case ID | SPM-42-TC06
Pre-conditions | npm run fixtures:spm42 has been run once at the start of this test pass (do not re-run it between cases - later cases use requests made in earlier ones). Logged in as Daniel Tan, assigned to the three events in Test data (all status Planning, no sessions). Orchard Seminar Room (ORC-SEM): setup 60 min, teardown 30 min. Changi Conference Centre (CBP-CONF): setup 120 min, teardown 90 min.
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'SPM42 Early Briefing' in the list 4. Click the 'Venue' tab 5. Find 'Orchard Seminar Room (ORC-SEM)' in the venue list and click its 'Request booking' button 6. Check only 'AM (07:00–12:00)' is ticked for 8 Mar 2027, read the 'Setup:' and 'Turnaround:' lines, then click 'Submit request' 7. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 8. Click 'SPM42 Late Show' in the list 9. Click the 'Venue' tab 10. Find 'Orchard Seminar Room (ORC-SEM)' in the venue list and click its 'Request booking' button 11. Check only 'Night (19:00–24:00)' is ticked for 9 Mar 2027, read the 'Setup:' and 'Turnaround:' lines, then click 'Submit request' 12. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 13. Click 'SPM42 Networking Evening' in the list 14. Click the 'Venue' tab 15. Find 'Changi Conference Centre (CBP-CONF)' in the venue list and click its 'Request booking' button 16. Check only 'PM (13:00–18:00)' and 'Night (19:00–24:00)' are ticked for 11 Mar 2027, read the 'Setup:' and 'Turnaround:' lines, then click 'Submit request'
Test Data | 1. spm42_early_briefing 'SPM42 Early Briefing', 8 Mar 2027 (2026-09-26 + 163) 09:00-12:00, Orchard Seminar Room, AM 2. spm42_late_show 'SPM42 Late Show', 9 Mar 2027 (2026-09-26 + 164) 19:00-22:00, Orchard Seminar Room, Night 3. spm42_networking 'SPM42 Networking Evening', 11 Mar 2027 (2026-09-26 + 166) 17:00-22:00, expects 120, Banquet, Changi Conference Centre, PM + Night
Expected Result | 1. 'Setup: 7 Mar 2027 Night (19:00–24:00)' and 'Turnaround: 8 Mar 2027 PM (13:00–18:00)'. 2. 'Setup: 9 Mar 2027 PM (13:00–18:00)' and 'Turnaround: 10 Mar 2027 AM (07:00–12:00)'. 3. 'Setup: 11 Mar 2027 AM (07:00–12:00)' and 'Turnaround: 12 Mar 2027 AM (07:00–12:00)' — one slot each end for a two-slot event, and 120 minutes of setup still takes only one slot. Each request is sent and holds exactly its chosen slots plus those two.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | 1. 'Setup: 7 Mar 2027 Night (19:00–24:00)' and 'Turnaround: 8 Mar 2027 PM (13:00–18:00)'. 2. 'Setup: 9 Mar 2027 PM (13:00–18:00)' and 'Turnaround: 10 Mar 2027 AM (07:00–12:00)'. 3. 'Setup: 11 Mar 2027 AM (07:00–12:00)' and 'Turnaround: 12 Mar 2027 AM (07:00–12:00)' — one slot each end for a two-slot event, and 120 minutes of setup still takes only one slot. Each request is sent and holds exactly its chosen slots plus those two.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | 1. SPM42 Early Briefing at Orchard Seminar Room: 'Setup: 7 Mar 2027 Night (19:00-24:00)' and 'Turnaround: 8 Mar 2027 PM (13:00-18:00)'. 2. SPM42 Late Show: 'Setup: 9 Mar 2027 PM (13:00-18:00)' and 'Turnaround: 10 Mar 2027 AM (07:00-12:00)'. 3. SPM42 Networking Evening at Changi Conference Centre: 'Setup: 11 Mar 2027 AM (07:00-12:00)' and 'Turnaround: 12 Mar 2027 AM (07:00-12:00)'. All three requests were sent.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Confirms both day-crossing directions: an AM event's setup takes the previous day's Night, and a Night event's turnaround takes the next day's AM (#123). Case 3 also confirms 120 minutes of setup still takes exactly one slot.
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## RETIRED – TC07
Item
Test Case ID | SPM-42-TC07
Pre-conditions | npm run fixtures:spm42 has been run once at the start of this test pass (do not re-run it between cases - later cases use requests made in earlier ones). Logged in as Daniel Tan, assigned to spm42_plain_pm 'SPM42 Plain Afternoon' (status Planning, 10 Mar 2027 (2026-09-26 + 165) 14:00-17:00, expects 30, Classroom, no sessions). Fixture venue 'SPM42 Plain Room' (SPM42-PLN) has setup 0 min and teardown 0 min.
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'SPM42 Plain Afternoon' in the list 4. Click the 'Venue' tab 5. Find 'SPM42 Plain Room (SPM42-PLN)' in the venue list and click its 'Request booking' button 6. Read the line under the slots 7. Tick 'Night (19:00–24:00)' as well, so 'PM (13:00–18:00)' and 'Night (19:00–24:00)' are both ticked for 10 Mar 2027 8. Check the line under the slots has not changed 9. Click 'Submit request' 10. Click 'Back to Venue' and read the request under 'Booking requests'
Test Data | Venue: SPM42 Plain Room, setup 0 min, teardown 0 min Date: 10 Mar 2027 (2026-09-26 + 165) Slots: PM, Night (the event only needs PM)
Expected Result | Before and after ticking Night, the line under the slots reads 'No setup or turnaround needed at this venue.' 'Booking request sent to Venue Staff.' is shown. Under 'Booking requests' the request reads '10 Mar 2027 · PM, Night (13:00–24:00)' — nothing before or after.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | Before and after ticking Night, the line under the slots reads 'No setup or turnaround needed at this venue.' 'Booking request sent to Venue Staff.' is shown. Under 'Booking requests' the request reads '10 Mar 2027 · PM, Night (13:00–24:00)' — nothing before or after.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | At SPM42 Plain Room the line under the slots read 'No setup or turnaround needed at this venue.' both before and after ticking Night, and no Setup or Turnaround line appeared. The request reads '10 Mar 2027 · PM, Night (13:00-24:00) · Classroom', Pending. Venue Staff's row for it carries no Setup or Turnaround line either.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## RETIRED – TC08
Item
Test Case ID | SPM-42-TC08
Pre-conditions | npm run fixtures:spm42 has been run once at the start of this test pass (do not re-run it between cases - later cases use requests made in earlier ones). Run this case before TC09, so Day 2 has no request yet. Logged in as Daniel Tan, assigned to spm42_three_sessions 'SPM42 Three-Session Forum' (Day 2: 2 Mar 2027 (2026-09-26 + 157) 14:00-17:00) and to 'SPM42 Refusal Checks' (7 Mar 2027 09:00-17:00, no sessions).
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'SPM42 Three-Session Forum' in the list 4. Click the 'Venue' tab 5. In the 'Session' drop-down, choose 'Day 2' 6. Find 'Orchard Studio (ORC-STU)' in the venue list and click its 'Request booking' button 7. Untick 'PM (13:00–18:00)', tick only 'AM (07:00–12:00)', then click 'Submit request' and read the message 8. Change the Date to 1 Mar 2027, tick only 'PM (13:00–18:00)', then click 'Submit request' and read the message 9. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 10. Click 'SPM42 Refusal Checks' in the list 11. Click the 'Venue' tab 12. Find 'Orchard Seminar Room (ORC-SEM)' in the venue list and click its 'Request booking' button 13. Untick 'PM (13:00–18:00)' so only 'AM (07:00–12:00)' is ticked for 7 Mar 2027, then click 'Submit request' and read the message
Test Data | Attempt 1: Day 2, 2 Mar 2027 AM (session runs in PM) Attempt 2: Day 2, 1 Mar 2027 PM (Day 1's date) Attempt 3: SPM42 Refusal Checks, 7 Mar 2027 AM only (event runs into PM)
Expected Result | Attempts 1 and 2 show 'The chosen slots do not cover the session's time (2 Mar 2027, 14:00–17:00).' Attempt 3 shows 'The chosen slots do not cover the event's time (7 Mar 2027, 09:00–17:00).' No request is created.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | Attempts 1 and 2 show 'The chosen slots do not cover the session's time (2 Mar 2027, 14:00–17:00).' Attempt 3 shows 'The chosen slots do not cover the event's time (7 Mar 2027, 09:00–17:00).' No request is created.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | Attempt 1 (Day 2, AM only): 'The chosen slots do not cover the session's time (2 Mar 2027, 14:00-17:00).' Attempt 2 (Day 2, moved to 1 Mar, PM): the same message, still naming the session's own date. Attempt 3 (SPM42 Refusal Checks, an event with no sessions, AM only): 'The chosen slots do not cover the event's time (7 Mar 2027, 09:00-17:00).' No request was created by any attempt.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Attempt 2 is the useful one: the refusal names the session's time even though the date was changed to another session's, so the check is against the chosen session rather than whatever date is in the box.
Executed by | TAN JORDAN
Date of Execution | 2026-10-01

## RETIRED – TC15
Item
Test Case ID | SPM-42-TC15
Pre-conditions | Seeded data: 'Product Showcase' has an Approved booking at Marina Auditorium (MAR-AUD, setup 60 min, teardown 30 min) on 21 Oct 2026 AM + PM, so its setup holds 20 Oct 2026 Night. Logged in as Daniel Tan, assigned to 'Keynote Rehearsal' (status Planning, 20 Oct 2026 (2026-09-26 + 24) 14:00-16:00, no sessions).
Test Steps | 1. Log in as daniel.tan@connectsphere.com / password123 2. Click 'All Events' in the sidebar (the list has no search box - use Ctrl+F to find the event) 3. Click 'Keynote Rehearsal' in the list 4. Click the 'Venue' tab 5. Find 'Marina Auditorium (MAR-AUD)' in the venue list and click its 'Request booking' button 6. Make sure only 'PM (13:00–18:00)' is ticked for 20 Oct 2026 7. Click 'Submit request' and read the message
Test Data | Requested: 20 Oct 2026 PM (its turnaround takes 20 Oct Night) Existing: Product Showcase, 21 Oct AM + PM (its setup takes 20 Oct Night)
Expected Result | Error 'Marina Auditorium is already booked for this time.' is shown, although the two events' own slots (20 Oct PM and 21 Oct AM + PM) do not overlap. No request is created.
Created By | Sammi Chua
Creation Date | 2026-10-01
Item
Actual Result | Error 'Marina Auditorium is already booked for this time.' is shown, although the two events' own slots (20 Oct PM and 21 Oct AM + PM) do not overlap. No request is created.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Sammi
Date of Execution | 2026-10-01
Item
Actual Result | Requesting Marina Auditorium for 20 Oct 2026 PM was refused with 'Marina Auditorium is already booked for this time.', although the two events' own slots (20 Oct PM and 21 Oct AM + PM) do not overlap - the clash is only through 20 Oct Night, which this request's turnaround and the existing booking's setup both need. No request was created.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | This is the case that proves setup and turnaround slots are held against other bookings, not merely displayed on the calendar.
Executed by | TAN JORDAN
Date of Execution | 2026-10-01