## Summary
Story | SPM-21: As a ConnectSphere user, I want to securely log in to the system so that I can access functionality appropriate to my role
Sheet | Test Case ID | Title | Linked AC | Type | Source
TC01 | SPM-21-TC01 | Valid credentials sign the user in and open the dashboard | AC1 | Positive | Acceptance Criteria
TC02 | SPM-21-TC02 | The signed-in chrome appears immediately, without a manual refresh | AC1 | Positive | Code
TC03 | SPM-21-TC03 | After signing in, the user is returned to the page they first asked for | AC1 | Positive | Code
TC04 | SPM-21-TC04 | The session survives a browser refresh | AC1, AC3 | Positive | Code
TC05 | SPM-21-TC05 | A wrong password is refused with an error message | AC2 | Negative | Acceptance Criteria
TC06 | SPM-21-TC06 | An unknown email is refused with the same message as a wrong password | AC2 | Negative | Code
TC07 | SPM-21-TC07 | An email that is not a valid address is refused with a message naming the problem | AC2 | Negative | Acceptance Criteria
TC08 | SPM-21-TC08 | An empty password is refused with a message naming the problem | AC2 | Boundary | Acceptance Criteria
TC09 | SPM-21-TC09 | A one-character password is treated as a wrong password, not a malformed one | AC2 | Boundary | Code
TC10 | SPM-21-TC10 | A deactivated account cannot log in, even with the correct password | AC2 | Negative | Code
TC11 | SPM-21-TC11 | An email typed with different capitalisation | AC1, AC2 | Boundary | Code
TC12 | SPM-21-TC12 | The signed-in user's role is named on the dashboard | AC3 | Positive | Acceptance Criteria
TC13 | SPM-21-TC13 | The navigation offered matches the role that is signed in | AC3 | Positive | Code
TC14 | SPM-21-TC14 | Logging out ends the session | AC3, AC4 | Negative | Code
TC15 | SPM-21-TC15 | A signed-out visitor cannot reach a signed-in page | AC4 | Negative | Acceptance Criteria
TC16 | SPM-21-TC16 | A Coordinator cannot raise an event request | AC4 | Negative | Acceptance Criteria
TC17 | SPM-21-TC17 | A stranger cannot give themselves a staff role when registering | AC4 | Negative | Code
TC18 | SPM-21-TC18 | An Organiser sees only their own client's events | AC4 | Negative | Code
TC19 | SPM-21-TC19 | A tampered session token is not accepted | AC4 | Negative | Code
AC | Acceptance Criterion |  |  | Covered by
AC1 | Given I have valid credentials, when I log in, then I am authenticated successfully. |  |  | SPM-21-TC01 SPM-21-TC02 SPM-21-TC03 SPM-21-TC04 SPM-21-TC11
AC2 | Given I enter invalid credentials, when I attempt to log in, then access is denied and an appropriate error message is displayed. |  |  | SPM-21-TC05 SPM-21-TC06 SPM-21-TC07 SPM-21-TC08 SPM-21-TC09 SPM-21-TC10 SPM-21-TC11
AC3 | Given I am logged in, when I access the system, then my role is identified. |  |  | SPM-21-TC04 SPM-21-TC12 SPM-21-TC13 SPM-21-TC14
AC4 | Given I am logged in, when I access a function that my role is not authorised for, then access is denied. |  |  | SPM-21-TC14 SPM-21-TC15 SPM-21-TC16 SPM-21-TC17 SPM-21-TC18 SPM-21-TC19
Code reviewed | src/app/api/auth/login/route.ts src/app/api/auth/me/route.ts src/app/login/page.tsx src/app/register/page.tsx src/app/dashboard/page.tsx src/lib/auth.ts src/lib/apiAuth.ts src/lib/session.ts src/lib/useCurrentUser.ts src/lib/roles.ts src/lib/validation/auth.ts src/lib/permissions.ts scripts/verify-login.ts

## TC01
Item
Test Case ID | SPM-21-TC01
Pre-conditions | Demo data is seeded. No one is signed in. On the "Log in" page.
Test Steps | 1. Enter "daniel.tan@connectsphere.com" into Email 2. Enter "password123" into Password 3. Click "Log in"
Test Data | Email: daniel.tan@connectsphere.com; Password: password123
Expected Result | The button shows "Logging in…" while the request is in flight. The browser moves to the Dashboard, headed "Welcome, Daniel Tan" with "Event Coordinator" beneath it, and the top bar shows the same role under the name. No error message is shown.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Browser moved to /dashboard. Page headed "Welcome, Daniel Tan" with "Event Coordinator" directly beneath it; the top bar also shows "Daniel Tan" over "Event Coordinator". No error alert. Sidebar: Dashboard, Review Queue, All Events, Venues, Equipment, Notifications.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Only informational alerts present (the teal "Internal view" note). The "Awaiting your review" cards render as skeletons for about a second before the seeded events appear - a loading state, not an error.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Browser moved to /dashboard. Page headed "Welcome, Daniel Tan" with "Event Coordinator" directly beneath it; the top bar also shows "Daniel Tan" over "Event Coordinator". No error alert. Sidebar: Dashboard, Review Queue, All Events, Venues, Equipment, Notifications.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | If im previously on events page, logged out and logged back in, i will get redirected to the events page again
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC02
Item
Test Case ID | SPM-21-TC02
Pre-conditions | No one is signed in. On the "Log in" page, where no sidebar is shown.
Test Steps | 1. Enter "rachel.ng@meridianfina.com" into Email 2. Enter "password123" into Password 3. Click "Log in" 4. Look at the sidebar and the top bar without reloading the page
Test Data | Email: rachel.ng@meridianfina.com; Password: password123
Expected Result | The sidebar appears straight away with Dashboard, My Events and Notifications, and the top bar shows Rachel Ng. No browser reload is needed to make the sidebar appear.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Before logging in the page had no sidebar at all. Immediately after clicking Log in - with no reload - the sidebar rendered "Dashboard, My Events, Notifications" and the top bar showed Rachel Ng. Header read "Welcome, Rachel Ng" / "Event Organiser".
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Confirms the onTokenChange fix in src/lib/session.ts: the already-mounted shell picks up the new session without a page reload.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Before logging in the page had no sidebar at all. Immediately after clicking Log in - with no reload - the sidebar rendered "Dashboard, My Events, Notifications" and the top bar showed Rachel Ng. Header read "Welcome, Rachel Ng" / "Event Organiser".
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC03
Item
Test Case ID | SPM-21-TC03
Pre-conditions | No one is signed in.
Test Steps | 1. Open the My Events page directly in the browser 2. Observe the page the browser lands on 3. Enter "rachel.ng@meridianfina.com" into Email 4. Enter "password123" into Password 5. Click "Log in"
Test Data | Email: rachel.ng@meridianfina.com; Password: password123
Expected Result | The browser lands on the "Log in" page showing the notice "Your session expired. Log in to continue where you left off." After logging in, the browser opens My Events, not the Dashboard.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Requesting My Events while signed out landed on /login?next=%2Fevents showing "Your session expired. Log in to continue where you left off." After logging in, the browser opened /events, headed "My events" - not the Dashboard.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Return path preserved through the ?next= parameter as specified in UI_DESIGN.md section 7.4.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Requesting My Events while signed out landed on /login?next=%2Fevents showing "Your session expired. Log in to continue where you left off." After logging in, the browser opened /events, headed "My events" - not the Dashboard.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC04
Item
Test Case ID | SPM-21-TC04
Pre-conditions | Signed in as Daniel Tan (daniel.tan@connectsphere.com / password123), on the Dashboard.
Test Steps | 1. Press F5 to reload the page 2. Wait for the page to finish loading
Test Data | Account: daniel.tan@connectsphere.com
Expected Result | The Dashboard reloads still signed in as Daniel Tan, still labelled "Event Coordinator". The browser is not sent back to the "Log in" page.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Before reload: "Welcome, Daniel Tan" / "Event Coordinator". After F5 the URL was still /dashboard, the header still read "Welcome, Daniel Tan" / "Event Coordinator", and the Coordinator sidebar was intact. No redirect to the login page.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Session token survives in localStorage; the role is re-fetched from /api/auth/me rather than trusted from the page.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Before reload: "Welcome, Daniel Tan" / "Event Coordinator". After F5 the URL was still /dashboard, the header still read "Welcome, Daniel Tan" / "Event Coordinator", and the Coordinator sidebar was intact. No redirect to the login page.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle
Date of Execution | 2026-09-20

## TC05
Item
Test Case ID | SPM-21-TC05
Pre-conditions | Demo data is seeded. No one is signed in. On the "Log in" page.
Test Steps | 1. Enter "daniel.tan@connectsphere.com" into Email 2. Enter "wrongpass" into Password 3. Click "Log in"
Test Data | Email: daniel.tan@connectsphere.com; Password: wrongpass
Expected Result | A red error message "Invalid email or password" is shown above the form. The browser stays on the "Log in" page and no sidebar appears.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Stayed on /login. A red alert reading exactly "Invalid email or password" appeared above the form. No sidebar appeared and no dashboard was reached.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | -
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Stayed on /login. A red alert reading exactly "Invalid email or password" appeared above the form. No sidebar appeared and no dashboard was reached.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | -
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC06
Item
Test Case ID | SPM-21-TC06
Pre-conditions | No account exists for nobody@connectsphere.com. No one is signed in. On the "Log in" page.
Test Steps | 1. Enter "nobody@connectsphere.com" into Email 2. Enter "password123" into Password 3. Click "Log in" 4. Compare the message with the one seen in TC05
Test Data | Email: nobody@connectsphere.com; Password: password123
Expected Result | The error message is "Invalid email or password" — word for word the same as TC05. Nothing on screen reveals whether the account exists.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Stayed on /login with the alert "Invalid email or password" - character for character the same message TC05 produced for a real account with a wrong password.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | No account enumeration: the screen gives away nothing about whether nobody@connectsphere.com exists.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Stayed on /login with the alert "Invalid email or password" - character for character the same message TC05 produced for a real account with a wrong password.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC07
Item
Test Case ID | SPM-21-TC07
Pre-conditions | No one is signed in. On the "Log in" page.
Test Steps | 1. Enter "daniel.tan" into Email 2. Enter "password123" into Password 3. Click "Log in"
Test Data | Email: daniel.tan; Password: password123
Expected Result | The message "Enter a valid email address" is shown against the Email field, which is outlined in red, so the user can see exactly which field to correct. The browser stays on the "Log in" page.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Stayed on /login. The message "Enter a valid email address" appeared directly under the Email field, with the field outlined in red. No generic banner.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Re-run after the fix. First run on 2026-09-20 FAILED, showing only "Validation failed" with nothing marking the field. src/app/login/page.tsx now maps the server's fieldErrors through readServerError(). See Open Questions #1.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Stayed on /login. The message "Enter a valid email address" appeared directly under the Email field, with the field outlined in red. No generic banner.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC08
Item
Test Case ID | SPM-21-TC08
Pre-conditions | No one is signed in. On the "Log in" page.
Test Steps | 1. Enter "daniel.tan@connectsphere.com" into Email 2. Leave Password empty 3. Click "Log in"
Test Data | Email: daniel.tan@connectsphere.com; Password: (empty)
Expected Result | The message "Enter your password" is shown against the Password field, which is outlined in red. The browser stays on the "Log in" page.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Stayed on /login. The message "Enter your password" appeared directly under the Password field, with the field outlined in red.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Re-run after the same fix; first run FAILED with a bare "Validation failed". loginSchema now carries a written message instead of Zod's default "String must contain at least 1 character(s)".
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Stayed on /login. The message "Enter your password" appeared directly under the Password field, with the field outlined in red.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC09
Item
Test Case ID | SPM-21-TC09
Pre-conditions | No one is signed in. On the "Log in" page.
Test Steps | 1. Enter "daniel.tan@connectsphere.com" into Email 2. Enter "x" into Password 3. Click "Log in"
Test Data | Email: daniel.tan@connectsphere.com; Password: x
Expected Result | The error message is "Invalid email or password" — the shortest allowed password is one character, so the attempt is checked as a credential rather than rejected as an empty field. The browser stays on the "Log in" page.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Stayed on /login with "Invalid email or password" - the same credential refusal as TC05, not the field-level error of TC07/TC08.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Confirms the boundary: loginSchema allows a one-character password, so a single character is checked as a credential rather than rejected as empty.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Stayed on /login with "Invalid email or password" - the same credential refusal as TC05, not the field-level error of TC07/TC08.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle
Date of Execution | 2026-09-20

## TC10
Item
Test Case ID | SPM-21-TC10
Pre-conditions | Marcus Wong (marcus.wong@connectsphere.com) has been deactivated: open Prisma Studio (npx prisma studio), find the row in Users and set Is Active to false. No one is signed in. On the "Log in" page.
Test Steps | 1. Enter "marcus.wong@connectsphere.com" into Email 2. Enter "password123" into Password 3. Click "Log in" 4. Afterwards, set Is Active back to true in Prisma Studio
Test Data | Email: marcus.wong@connectsphere.com; Password: password123; Is Active: false
Expected Result | The error message "This account has been deactivated. Contact your ConnectSphere administrator." is shown. The browser stays on the "Log in" page and no dashboard is reached.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | With Marcus Wong set to Is Active = false, logging in with the correct password stayed on /login and showed "This account has been deactivated. Contact your ConnectSphere administrator." No session was created and no sidebar appeared.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Account reactivated after the run and re-verified: marcus.wong logs in normally again. Note this message does confirm the account exists - a deliberate trade documented in src/app/api/auth/login/route.ts.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | showed "This account has been deactivated. Contact your ConnectSphere administrator." No session was created and no sidebar appeared.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC11
Item
Test Case ID | SPM-21-TC11
Pre-conditions | Demo data is seeded. No one is signed in. On the "Log in" page.
Test Steps | 1. Enter "Daniel.Tan@connectsphere.com" into Email 2. Enter "password123" into Password 3. Click "Log in"
Test Data | Email: Daniel.Tan@connectsphere.com (same address as TC01, different capitalisation); Password: password123
Expected Result | The user is signed in and the Dashboard opens, headed "Welcome, Daniel Tan" — an email address is not case sensitive, so this is the same account as TC01.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Signed in successfully. The browser moved to /dashboard headed "Welcome, Daniel Tan" / "Event Coordinator" - the same account TC01 reaches with the all-lowercase address.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Re-run after the fix. First run on 2026-09-20 FAILED with "Invalid email or password". loginSchema and registerSchema now trim and lower-case the address before it is checked or stored. See Open Questions #2.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Signed in successfully. The browser moved to /dashboard headed "Welcome, Daniel Tan" / "Event Coordinator" - the same account TC01 reaches with the all-lowercase address.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC12
Item
Test Case ID | SPM-21-TC12
Pre-conditions | Demo data is seeded. No one is signed in.
Test Steps | 1. Log in as daniel.tan@connectsphere.com with password123 2. Read the subtitle under the welcome heading 3. Log out, then log in as marcus.wong@connectsphere.com with password123 4. Read the subtitle under the welcome heading again
Test Data | Accounts: daniel.tan@connectsphere.com (Coordinator), marcus.wong@connectsphere.com (Venue Staff); Password: password123
Expected Result | Daniel Tan's dashboard is headed "Welcome, Daniel Tan", subtitled "Event Coordinator" and the section heading reads "Awaiting your review". Marcus Wong's dashboard is headed "Welcome, Marcus Wong", subtitled "Venue Staff" and the section heading reads "Upcoming events".
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Daniel Tan: headed "Welcome, Daniel Tan", subtitled "Event Coordinator", section heading "Awaiting your review". Marcus Wong: headed "Welcome, Marcus Wong", subtitled "Venue Staff", section heading "Upcoming events".
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The role is identified in two places - the page subtitle and the top bar - and the dashboard content changes with it.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Daniel Tan: headed "Welcome, Daniel Tan", subtitled "Event Coordinator", section heading "Awaiting your review". Marcus Wong: headed "Welcome, Marcus Wong", subtitled "Venue Staff", section heading "Upcoming events".
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC13
Item
Test Case ID | SPM-21-TC13
Pre-conditions | Demo data is seeded. No one is signed in.
Test Steps | 1. Log in as rachel.ng@meridianfina.com with password123 2. Write down every item in the sidebar 3. Log out, then log in as grace.lim@connectsphere.com with password123 4. Write down every item in the sidebar
Test Data | Accounts: rachel.ng@meridianfina.com (Organiser), grace.lim@connectsphere.com (Operations Manager); Password: password123
Expected Result | Rachel Ng's sidebar reads Dashboard, My Events, Notifications. Grace Lim's sidebar reads Dashboard, Assignments, All Events, Notifications. The page layout, colours and top bar are identical for both — only the list of items differs.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Rachel Ng (Organiser): Dashboard, My Events, Notifications. Grace Lim (Operations Manager): Dashboard, Assignments, All Events, Notifications. Same chrome, same layout; header read "Welcome, Grace Lim" / "Operations Manager".
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Navigation comes from NAV_BY_ROLE in src/lib/roles.ts. Note several of these items point at screens that are not built yet - see Open Questions #4.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Rachel Ng (Event Organiser): Dashboard, My Events, Notifications. Grace Lim (Operations Manager): Dashboard, Assignments, All Events, Notifications. Same chrome, same layout; header read "Welcome, Grace Lim" / "Operations Manager".
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC14
Item
Test Case ID | SPM-21-TC14
Pre-conditions | Signed in as Daniel Tan (daniel.tan@connectsphere.com / password123), on the Dashboard.
Test Steps | 1. Click the account control in the top bar 2. Click "Log out" 3. Open the Dashboard directly in the browser
Test Data | Account: daniel.tan@connectsphere.com
Expected Result | Logging out returns the browser to the "Log in" page and the sidebar disappears. Opening the Dashboard again lands back on "Log in" instead of showing Daniel Tan's dashboard.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Clicking Log out returned the browser to /login/dashboard and the sidebar disappeared. Asking for the Dashboard again landed straight back on the login page.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | clearToken() notifies every mounted useCurrentUser(), so the chrome drops the session immediately rather than on the next reload.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Clicking Log out returned the browser to /login/dashboard and the sidebar disappeared. Asking for the Dashboard again landed straight back on the login page.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC15
Item
Test Case ID | SPM-21-TC15
Pre-conditions | No one is signed in.
Test Steps | 1. Open the Dashboard directly in the browser 2. Observe where the browser lands
Test Data | Page requested: Dashboard, with no session
Expected Result | The browser is sent to the "Log in" page with the notice "Your session expired. Log in to continue where you left off." No dashboard content, event list or role name is shown at any point.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Requesting the Dashboard with no session landed on /login/dashboard showing "Your session expired. Log in to continue where you left off." No role name and no event title appeared anywhere on the page.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Checked the whole page body for leaked role names and event headings - none present at any point.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Requesting the Dashboard with no session landed on /login/dashboard showing "Your session expired. Log in to continue where you left off." No role name and no event title appeared anywhere on the page.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC16
Item
Test Case ID | SPM-21-TC16
Pre-conditions | Signed in as Daniel Tan (daniel.tan@connectsphere.com / password123), a Coordinator. The sidebar offers no "New request" action.
Test Steps | 1. Open the "New event request" page directly in the browser 2. Enter "Coordinator authorisation check" into Event name 3. Enter "Checking that only an Organiser may raise a request" into Purpose 4. Choose "Conference" as the Category 5. Enter a start and end date and time in the future 6. Enter "50" into Expected attendance 7. Click "Save draft"
Test Data | Account: daniel.tan@connectsphere.com (Coordinator); Event name: Coordinator authorisation check; Expected attendance: 50
Expected Result | The error message "Only an Event Organiser can raise an event request" is shown above the form. The browser stays on the form and no draft is created — opening All Events afterwards shows no event named "Coordinator authorisation check".
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | The form submitted and the browser stayed on /events/new with the alert "Only an Event Organiser can raise an event request". Opening All Events afterwards showed no event named "Coordinator authorisation check".
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The page has no client-side role gate, so the refusal comes from the server and is surfaced on the form. Nothing was written to the database.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | The form submitted and the browser stayed on /events/new with the alert "Only an Event Organiser can raise an event request". Opening All Events afterwards showed no event named "Coordinator authorisation check".
Pass/Fail/Not Executed/Blocked | Pass
Remarks | upon clicking submit request, Only an Event Organiser can raise an event request error message is shown at the top but the cursor doesnt move to the top
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC17
Item
Test Case ID | SPM-21-TC17
Pre-conditions | No one is signed in. On the "Register" page.
Test Steps | 1. Open the Role dropdown 2. Read every option offered
Test Data | Page: Register
Expected Result | The dropdown offers exactly two options: "Event Organiser" and "Attendee". Event Coordinator, Operations Manager, Venue Staff and Technical Support are not offered, so a staff account cannot be created by self-registration.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | The Role dropdown offered exactly two options: "Event Organiser" and "Attendee". No Coordinator, Operations Manager, Venue Staff or Technical Support option was present.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Driven by SELF_REGISTERABLE_ROLES in src/lib/roles.ts, which the register route also enforces server-side - the list is not merely hidden in the UI.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | The Role dropdown offered exactly two options: "Event Organiser" and "Attendee". No Coordinator, Operations Manager, Venue Staff or Technical Support option was present.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC18
Item
Test Case ID | SPM-21-TC18
Pre-conditions | Signed in as Rachel Ng (rachel.ng@meridianfina.com / password123), an Organiser at Meridian Financial Group. Budi Santoso (budi.santoso@nusantaratec.com) is an Organiser at Nusantara Tech Labs and has events of his own.
Test Steps | 1. Open My Events 2. Read the title and client of every event listed 3. Log out and log in as budi.santoso@nusantaratec.com with password123 4. Open My Events and compare the two lists
Test Data | Accounts: rachel.ng@meridianfina.com (Meridian Financial Group), budi.santoso@nusantaratec.com (Nusantara Tech Labs); Password: password123
Expected Result | Rachel Ng's list contains only Meridian Financial Group events. Budi Santoso's list contains only Nusantara Tech Labs events. Neither list contains any event belonging to the other client.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | Rachel Ng's My Events listed four events, all Meridian Financial Group (Q1 Investor Update draft, Graduate Recruitment Evening, Compliance Training, Wealth Management Forum). Budi Santoso's listed three, all Nusantara Tech Labs (Product Launch, Overnight Hackathon, Developer Summit). No row appeared in both lists.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Compared the two lists row by row; the intersection was empty. This is a relationship refusal rather than a role one - see Open Questions #5.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | Rachel Ng's My Events listed four events, all Meridian Financial Group (Q1 Investor Update draft, Graduate Recruitment Evening, Compliance Training, Wealth Management Forum). Budi Santoso's listed three, all Nusantara Tech Labs (Product Launch, Overnight Hackathon, Developer Summit). No row appeared in both lists.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20

## TC19
Item
Test Case ID | SPM-21-TC19
Pre-conditions | Signed in as Daniel Tan (daniel.tan@connectsphere.com / password123), on the Dashboard.
Test Steps | 1. Open the browser's developer tools and go to Application, then Local Storage 2. Change the last five characters of the value stored under "connectsphere_token" 3. Reload the Dashboard
Test Data | Stored key: connectsphere_token, with its last five characters altered
Expected Result | The browser is sent to the "Log in" page. No dashboard content or role name is shown — an altered token is treated as no session at all, not as a valid one.
Created By | TAN JORDAN
Creation Date | 2026-09-20
Item
Actual Result | After altering the last five characters of connectsphere_token in Local Storage and reloading, the browser was sent to /login?next=%2Fdashboard. No role name and no dashboard content appeared.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The signature no longer verifies, so getActor() returns null and the route answers 401 - an altered token is treated as no session, never as a valid one.
Executed by | TAN JORDAN
Date of Execution | 2026-09-20
Item
Actual Result | "The browser is sent to the ""Log in"" page with "Your session expired. Log in to continue where you left off." above the email
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-09-20