## Summary
Story | SPM-44: As the system, I want to detect overlapping venue bookings so that a venue cannot be double-booked for incompatible events
Sheet | Test Case ID | Title | Linked AC | Type | Source
TC01 | SPM-44-TC01 | A slot already held by an approved booking is refused, and the booking is named | AC1, AC3, AC5, AC9 | Negative | Acceptance Criteria
TC02 | SPM-44-TC02 | A different slot on the same day at the same venue is allowed | AC2, AC10 | Positive | Acceptance Criteria
TC03 | SPM-44-TC03 | An event's own booking does not conflict with itself | AC1, AC10 | Boundary | Code
TC04 | SPM-44-TC04 | A slot already held by another event's pending request is refused | AC4, AC5, AC9 | Negative | Acceptance Criteria
TC05 | SPM-44-TC05 | A rejected booking does not hold the slot | AC7, AC10 | Positive | Acceptance Criteria
TC06 | SPM-44-TC06 | A cancelled (withdrawn or released) booking does not hold the slot | AC7, AC10 | Positive | Acceptance Criteria
TC07 | SPM-44-TC07 | A different slot IS refused when the other booking's setup occupies it | AC2, AC5, AC9 | Boundary | Acceptance Criteria
TC08 | SPM-44-TC08 | A recorded unavailable period blocks a request, and its reason and dates are shown | AC8, AC9 | Negative | Acceptance Criteria
TC09 | SPM-44-TC09 | The venue search screen hides a venue whose slot is taken | AC1, AC3 | Positive | Code
TC10 | SPM-44-TC10 | A confirmed booking cannot be approved over another confirmed booking | AC6 | Negative | Acceptance Criteria
TC11 | SPM-44-TC11 | A Night booking's turnaround blocks the NEXT morning's AM slot | AC2, AC3, AC5, AC9 | Boundary | Acceptance Criteria
AC | Acceptance Criterion |  |  | Covered by
AC1 | The system checks existing bookings when a venue booking is requested. |  |  | SPM-44-TC01 SPM-44-TC03 SPM-44-TC09
AC2 | Conflict checking is performed per fixed slot (AM, PM, Night); two bookings in different slots on the same day for the same venue do not conflict unless one's setup or turnaround requirement occupies the other's slot. |  |  | SPM-44-TC02 SPM-44-TC07 SPM-44-TC11
AC3 | An overlapping confirmed booking is detected. |  |  | SPM-44-TC01 SPM-44-TC09 SPM-44-TC11
AC4 | An overlapping pending booking request is detected: only one active pending request or confirmed booking may exist for the same venue and slot. |  |  | SPM-44-TC04
AC5 | A booking request cannot be submitted if it conflicts with an existing pending request or confirmed booking. |  |  | SPM-44-TC01 SPM-44-TC04 SPM-44-TC07 SPM-44-TC11
AC6 | A booking request cannot be confirmed if it conflicts with an existing confirmed booking. |  |  | SPM-44-TC10
AC7 | A rejected, withdrawn or released booking does not count as a conflict. |  |  | SPM-44-TC05 SPM-44-TC06
AC8 | Venue unavailability is treated as a conflict. |  |  | SPM-44-TC08
AC9 | The conflicting booking or unavailable period is identified to the authorised user. |  |  | SPM-44-TC01 SPM-44-TC04 SPM-44-TC07 SPM-44-TC08 SPM-44-TC11
AC10 | Non-overlapping bookings are allowed. |  |  | SPM-44-TC02 SPM-44-TC03 SPM-44-TC05 SPM-44-TC06
Code reviewed | src/lib/venueConflict.ts src/lib/__tests__/venueConflict.test.ts src/lib/venueBookingRequest.ts src/lib/venueSearch.ts src/lib/venueSlots.ts src/app/api/events/[id]/venue-bookings/route.ts src/app/events/[id]/venue/page.tsx src/app/events/[id]/booking/new/page.tsx scripts/seed-spm44.ts prisma/seed.ts docs/CUSTOMER_CLARIFICATIONS.md

## TC01
Item
Test Case ID | SPM-44-TC01
Pre-conditions | npm run fixtures:spm44 has been run. 'SPM44 Approved Holder' holds an APPROVED booking at SPM44 Conflict Room (SPM44-PLN) on 5 Apr 2027, PM. 'SPM44 Clash With Approved' runs 5 Apr 2027 14:00-16:00 and has no booking. SPM44-PLN needs no setup or turnaround time. Logged in as Event Coordinator Daniel Tan (daniel.tan@connectsphere.com / password123), assigned to 'SPM44 Clash With Approved'. This case changes no data, but run the fixtures again afterwards if a later case has already run.
Test Steps | 1. Click 'All Events' in the sidebar 2. Click 'SPM44 Clash With Approved' in the list 3. Click the 'Venue' tab 4. Find 'SPM44 Conflict Room (SPM44-PLN)' in the venue list and click its 'Request booking' button 5. Click 'Submit request'
Test Data | Event: SPM44 Clash With Approved (5 Apr 2027, 14:00-16:00) Venue: SPM44 Conflict Room (SPM44-PLN) Slot offered: PM (13:00-18:00), already ticked In the way: SPM44 Approved Holder, approved, same room and slot
Expected Result | Step 4: The booking request screen opens with the Date 5 Apr 2027 and only 'PM (13:00–18:00)' ticked. Step 5: The request is refused with 'SPM44 Conflict Room is already booked for EVT-… SPM44 Approved Holder on 5 Apr 2027, PM.' — naming the event in the way, not just the fact of it. No request is created, and no new row appears under 'Booking requests'.
Created By | TAN JORDAN
Creation Date | 2026-10-02
Item
Actual Result | The booking screen opened on 5 Apr 2027 with only PM ticked. Submitting was refused with 'SPM44 Conflict Room is already booked for EVT-....... SPM44 Approved Holder on 5 Apr 2027, PM.' No request was created.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The refusal names the event in the way, which is the whole of AC9. Before SPM-44 the same attempt said only '... is already booked for this time.'
Executed by | TAN JORDAN
Date of Execution | 2026-10-02
Item
Actual Result | The request is refused with 'SPM44 Conflict Room is already booked for EVT-… SPM44 Approved Holder on 5 Apr 2027, PM.' — naming the event in the way, not just the fact of it. No request is created, and no new row appears under 'Booking requests'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kayalvizhi
Date of Execution | 2026-10-03

## TC02
Item
Test Case ID | SPM-44-TC02
Pre-conditions | npm run fixtures:spm44 has been run. 'SPM44 Approved Holder' holds an APPROVED booking at SPM44 Conflict Room on 5 Apr 2027, PM. 'SPM44 Adjacent Slot' runs 5 Apr 2027 09:00-11:00 (AM) and has no booking. SPM44-PLN needs no setup or turnaround time, so the PM booking holds PM alone. Logged in as Daniel Tan, assigned to 'SPM44 Adjacent Slot'. This case creates a booking request — run npm run fixtures:spm44 afterwards.
Test Steps | 1. Click 'All Events' in the sidebar 2. Click 'SPM44 Adjacent Slot' in the list 3. Click the 'Venue' tab 4. Find 'SPM44 Conflict Room (SPM44-PLN)' in the venue list and click its 'Request booking' button 5. Click 'Submit request' 6. Click 'Back to Venue'
Test Data | Event: SPM44 Adjacent Slot (5 Apr 2027, 09:00-11:00) Venue: SPM44 Conflict Room (SPM44-PLN) Slot: AM (07:00-12:00) Same room and day as the approved PM booking
Expected Result | Step 4: The booking request screen opens with the Date 5 Apr 2027 and only 'AM (07:00–12:00)' ticked. Step 5: 'Booking request sent to Venue Staff.' is shown — the approved PM booking does not block AM at a venue with no setup or turnaround time. Step 6: The request is listed under 'Booking requests' as '5 Apr 2027 · AM (07:00–12:00) · Classroom' with the status badge 'Pending'.
Created By | TAN JORDAN
Creation Date | 2026-10-02
Item
Actual Result | The booking screen opened on 5 Apr 2027 with only AM ticked. 'Booking request sent to Venue Staff.' was shown, and the request is listed as '5 Apr 2027 · AM (07:00-12:00) · Classroom' with the badge Pending - the approved PM booking at the same room on the same day did not block it.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Only demonstrable at a venue with no setup or turnaround time, which is why the fixtures create SPM44 Conflict Room rather than reuse a seeded room.
Executed by | TAN JORDAN
Date of Execution | 2026-10-02
Item
Actual Result | Step 4: The booking request screen opens with the Date 5 Apr 2027 and only 'AM (07:00–12:00)' ticked. Step 5: 'Booking request sent to Venue Staff.' is shown — the approved PM booking does not block AM at a venue with no setup or turnaround time. Step 6: The request is listed under 'Booking requests' as '5 Apr 2027 · AM (07:00–12:00) · Classroom' with the status badge 'Pending'.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kayalvizhi
Date of Execution | 2026-10-03

## TC03
Item
Test Case ID | SPM-44-TC03
Pre-conditions | SPM-44-TC02 has just been run (so 'SPM44 Adjacent Slot' now holds a pending request at SPM44 Conflict Room on 5 Apr 2027, AM) and the fixtures have NOT been reset since. Logged in as Daniel Tan, assigned to 'SPM44 Adjacent Slot'. Run npm run fixtures:spm44 after this case.
Test Steps | 1. Click 'All Events' in the sidebar 2. Click 'SPM44 Adjacent Slot' in the list 3. Click the 'Venue' tab 4. Find 'SPM44 Conflict Room (SPM44-PLN)' in the venue list and read its status chip
Test Data | Event: SPM44 Adjacent Slot, which already holds a pending AM request at this room
Expected Result | Step 4: SPM44 Conflict Room is still shown as 'Suitable' with a 'Request booking' button — an event's own pending request is not reported as a conflict with itself. The pending request it already holds is listed under 'Booking requests' above.
Created By | TAN JORDAN
Creation Date | 2026-10-02
Item
Actual Result | With its own pending AM request already in place, SPM44 Conflict Room was still shown as 'Suitable' with a 'Request booking' button on the event's own Venue tab.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | TAN JORDAN
Date of Execution | 2026-10-02
Item
Actual Result | With its own pending AM request already in place, SPM44 Conflict Room was still shown as 'Suitable' with a 'Request booking' button on the event's own Venue tab.
Pass/Fail/Not Executed/Blocked | Fail
Remarks | This Test Case is invalid AC5 states that: A booking request cannot be submitted if it conflicts with an existing pending request or confirmed booking.Right now it allows user to request same venue for same timeslot for the same event twice, which goes against the AC.
Executed by | Kayalvizhi
Date of Execution | 2026-10-03
Item
Actual Result | Step 3: The request from TC02 was listed under 'Booking requests' as '5 Apr 2027 · AM (07:00–12:00) · Classroom', Pending. Step 4: SPM44 Conflict Room was still shown as 'Suitable' with a 'Request booking' button; the request screen opened on 5 Apr 2027 with only AM ticked. Step 5: Submitting was refused with 'This event already has a pending request for SPM44 Conflict Room on 5 Apr 2027 · AM (07:00–12:00).' Step 6: Cancel returned to the Venue tab, which still listed exactly one request for 5 Apr 2027 · AM.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Rewritten after review on PR #37 (kayalvizhi24). The earlier version of this case only checked that the button was still shown, and passed on 2026-10-02 - but submitting would have created a second pending request, because the event's own bookings are exempt from the clash check. findDuplicateRequest() now refuses the repeat; two different sessions of one event may still share a room.
Executed by | TAN JORDAN
Date of Execution | 2026-10-06
Item
Actual Result | Step 3: The request from TC02 was listed under 'Booking requests' as '5 Apr 2027 · AM (07:00–12:00) · Classroom', Pending. Step 4: SPM44 Conflict Room was still shown as 'Suitable' with a 'Request booking' button; the request screen opened on 5 Apr 2027 with only AM ticked. Step 5: Submitting was refused with 'This event already has a pending request for SPM44 Conflict Room on 5 Apr 2027 · AM (07:00–12:00).' Step 6: Cancel returned to the Venue tab, which still listed exactly one request for 5 Apr 2027 · AM.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Janelle Ip
Date of Execution | 2026-10-08

## TC04
Item
Test Case ID | SPM-44-TC04
Pre-conditions | npm run fixtures:spm44 has been run. 'SPM44 Pending Holder' holds a PENDING booking request at SPM44 Conflict Room on 6 Apr 2027, PM. 'SPM44 Clash With Pending' runs 6 Apr 2027 14:00-16:00 and has no booking. Logged in as Daniel Tan, assigned to 'SPM44 Clash With Pending'.
Test Steps | 1. Click 'All Events' in the sidebar 2. Click 'SPM44 Clash With Pending' in the list 3. Click the 'Venue' tab 4. Find 'SPM44 Conflict Room (SPM44-PLN)' in the venue list and click its 'Request booking' button 5. Click 'Submit request'
Test Data | Event: SPM44 Clash With Pending (6 Apr 2027, 14:00-16:00) Venue: SPM44 Conflict Room (SPM44-PLN) Slot: PM (13:00-18:00) In the way: SPM44 Pending Holder, pending, same room and slot
Expected Result | Step 5: The request is refused with 'SPM44 Conflict Room is on hold for EVT-… SPM44 Pending Holder on 6 Apr 2027, PM.' — a hold is named as a hold, not as a booking, so the coordinator knows it may still be released. No request is created.
Created By | TAN JORDAN
Creation Date | 2026-10-02
Item
Actual Result | Submitting was refused with 'SPM44 Conflict Room is on hold for EVT-000844 SPM44 Pending Holder on 6 Apr 2027, PM.' No request was created.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | A hold is worded as a hold rather than a booking, so the coordinator can tell that it may still be released (#41).
Executed by | TAN JORDAN
Date of Execution | 2026-10-02
Item
Actual Result | Submitting was refused with 'SPM44 Conflict Room is on hold for EVT-000844 SPM44 Pending Holder on 6 Apr 2027, PM.' No request was created.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | A hold is worded as a hold rather than a booking, so the coordinator can tell that it may still be released (#41).
Executed by | Kayalvizhi
Date of Execution | 2026-10-03

## TC05
Item
Test Case ID | SPM-44-TC05
Pre-conditions | npm run fixtures:spm44 has been run. 'SPM44 Rejected Holder' has a REJECTED booking at SPM44 Conflict Room on 7 Apr 2027, PM. 'SPM44 After Rejected' runs 7 Apr 2027 14:00-16:00 — the same room and slot. Logged in as Daniel Tan, assigned to 'SPM44 After Rejected'. This case creates a booking request — run npm run fixtures:spm44 afterwards.
Test Steps | 1. Click 'All Events' in the sidebar 2. Click 'SPM44 After Rejected' in the list 3. Click the 'Venue' tab 4. Find 'SPM44 Conflict Room (SPM44-PLN)' in the venue list and click its 'Request booking' button 5. Click 'Submit request' 6. Click 'Back to Venue'
Test Data | Event: SPM44 After Rejected (7 Apr 2027, 14:00-16:00) Venue: SPM44 Conflict Room (SPM44-PLN) In the way: nothing — SPM44 Rejected Holder's booking for the same slot was rejected
Expected Result | Step 5: 'Booking request sent to Venue Staff.' is shown — a rejected booking holds nothing. Step 6: The request is listed under 'Booking requests' as '7 Apr 2027 · PM (13:00–18:00) · Classroom' with the status badge 'Pending'.
Created By | TAN JORDAN
Creation Date | 2026-10-02
Item
Actual Result | 'Booking request sent to Venue Staff.' was shown and the request is listed as '7 Apr 2027 · PM (13:00-18:00) · Classroom', Pending - the rejected booking for the same room and slot held nothing.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | TAN JORDAN
Date of Execution | 2026-10-02
Item
Actual Result | 'Booking request sent to Venue Staff.' was shown and the request is listed as '7 Apr 2027 · PM (13:00-18:00) · Classroom', Pending - the rejected booking for the same room and slot held nothing.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | NA
Executed by | Kayalvizhi
Date of Execution | 2026-10-03

## TC06
Item
Test Case ID | SPM-44-TC06
Pre-conditions | npm run fixtures:spm44 has been run. 'SPM44 Cancelled Holder' has a CANCELLED booking at SPM44 Conflict Room on 8 Apr 2027, PM — the status the system stores for a withdrawn or released booking. 'SPM44 After Cancelled' runs 8 Apr 2027 14:00-16:00. Logged in as Daniel Tan, assigned to 'SPM44 After Cancelled'. This case creates a booking request — run npm run fixtures:spm44 afterwards.
Test Steps | 1. Click 'All Events' in the sidebar 2. Click 'SPM44 After Cancelled' in the list 3. Click the 'Venue' tab 4. Find 'SPM44 Conflict Room (SPM44-PLN)' in the venue list and click its 'Request booking' button 5. Click 'Submit request' 6. Click 'Back to Venue'
Test Data | Event: SPM44 After Cancelled (8 Apr 2027, 14:00-16:00) Venue: SPM44 Conflict Room (SPM44-PLN) In the way: nothing — SPM44 Cancelled Holder's booking for the same slot was cancelled
Expected Result | Step 5: 'Booking request sent to Venue Staff.' is shown. Step 6: The request is listed under 'Booking requests' as '8 Apr 2027 · PM (13:00–18:00) · Classroom' with the status badge 'Pending'.
Created By | TAN JORDAN
Creation Date | 2026-10-02
Item
Actual Result | 'Booking request sent to Venue Staff.' was shown and the request is listed as '8 Apr 2027 · PM (13:00-18:00) · Classroom', Pending - the cancelled booking for the same room and slot held nothing.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | 'Cancelled' is the status the schema stores for the customer's 'withdrawn' and 'released'; there is no separate value for either.
Executed by | TAN JORDAN
Date of Execution | 2026-10-02
Item
Actual Result | 'Booking request sent to Venue Staff.' was shown and the request is listed as '8 Apr 2027 · PM (13:00-18:00) · Classroom', Pending - the cancelled booking for the same room and slot held nothing.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | 'Cancelled' is the status the schema stores for the customer's 'withdrawn' and 'released'; there is no separate value for either.
Executed by | Kayalvizhi
Date of Execution | 2026-10-03

## TC07
Item
Test Case ID | SPM-44-TC07
Pre-conditions | npm run fixtures:spm44 has been run. Orchard Seminar Room (ORC-SEM) records 60 minutes of setup and 30 of teardown, so a booking there also takes one whole adjacent slot either side. 'SPM44 Setup Holder' holds an APPROVED booking at ORC-SEM on 9 Apr 2027, PM — whose setup therefore takes that morning's AM. 'SPM44 Setup Clash' runs 9 Apr 2027 09:00-11:00 (AM). Logged in as Daniel Tan, assigned to 'SPM44 Setup Clash'.
Test Steps | 1. Click 'All Events' in the sidebar 2. Click 'SPM44 Setup Clash' in the list 3. Click the 'Venue' tab 4. Find 'Orchard Seminar Room (ORC-SEM)' in the venue list and click its 'Request booking' button 5. Click 'Submit request'
Test Data | Event: SPM44 Setup Clash (9 Apr 2027, 09:00-11:00, AM) Venue: Orchard Seminar Room (ORC-SEM), setup 60 min, teardown 30 min In the way: SPM44 Setup Holder's approved PM booking, whose setup takes AM
Expected Result | Step 5: The request is refused with 'Orchard Seminar Room is already booked for EVT-… SPM44 Setup Holder on 9 Apr 2027, AM–PM.' — AM and PM are different slots, so this is the exception in AC2: at a venue with preparation time the two requests reach into each other's slots. Both are named, because both are genuinely contested — the holder's setup takes AM, and this request's own turnaround takes PM. No request is created.
Created By | TAN JORDAN
Creation Date | 2026-10-02
Item
Actual Result | Submitting the AM request was refused with 'Orchard Seminar Room is already booked for EVT-000850 SPM44 Setup Holder on 9 Apr 2027, AM-PM.' No request was created.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The case first expected 'AM' alone. Both slots are genuinely contested and the message is right: the holder's setup takes AM, and this request's own turnaround takes PM. The expected result was corrected to match before this run was recorded.
Executed by | TAN JORDAN
Date of Execution | 2026-10-02
Item
Actual Result | Submitting the AM request was refused with 'Orchard Seminar Room is already booked for EVT-000850 SPM44 Setup Holder on 9 Apr 2027, AM-PM.' No request was created.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The case first expected 'AM' alone. Both slots are genuinely contested and the message is right: the holder's setup takes AM, and this request's own turnaround takes PM. The expected result was corrected to match before this run was recorded.
Executed by | Kayalvizhi
Date of Execution | 2026-10-03

## TC08
Item
Test Case ID | SPM-44-TC08
Pre-conditions | npm run fixtures:spm44 has been run. SPM44 Conflict Room is recorded unavailable for maintenance from 20 Apr 2027 to 21 Apr 2027 inclusive. 'SPM44 Blocked Room' runs 20 Apr 2027 09:00-11:00 (AM) and has no booking. Logged in as Daniel Tan, assigned to 'SPM44 Blocked Room'.
Test Steps | 1. Click 'All Events' in the sidebar 2. Click 'SPM44 Blocked Room' in the list 3. Click the 'Venue' tab 4. Find 'SPM44 Conflict Room (SPM44-PLN)' in the venue list and click its 'Request booking' button 5. Click 'Submit request'
Test Data | Event: SPM44 Blocked Room (20 Apr 2027, 09:00-11:00) Venue: SPM44 Conflict Room (SPM44-PLN) In the way: maintenance, 20-21 Apr 2027
Expected Result | Step 5: The request is refused with 'SPM44 Conflict Room is unavailable at this time (maintenance, 20 Apr 2027 AM – 21 Apr 2027 Night).' — the reason and the WHOLE closure, not only the slot asked for, so the coordinator can see the room is out for two days and pick another date. No request is created.
Created By | TAN JORDAN
Creation Date | 2026-10-02
Item
Actual Result | Submitting was refused with 'SPM44 Conflict Room is unavailable at this time (maintenance, 20 Apr 2027 AM - 21 Apr 2027 Night).' No request was created.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The message gives the whole closure, not just the slot asked for, so the coordinator can see the room is out for two days and choose another date.
Executed by | TAN JORDAN
Date of Execution | 2026-10-02
Item
Actual Result | Submitting was refused with 'SPM44 Conflict Room is unavailable at this time (maintenance, 20 Apr 2027 AM - 21 Apr 2027 Night).' No request was created.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The message gives the whole closure, not just the slot asked for, so the coordinator can see the room is out for two days and choose another date.
Executed by | Kayalvizhi
Date of Execution | 2026-10-03

## TC09
Item
Test Case ID | SPM-44-TC09
Pre-conditions | npm run fixtures:spm44 has been run. 'SPM44 Approved Holder' holds an APPROVED booking at SPM44 Conflict Room on 5 Apr 2027, PM. Logged in as Daniel Tan, assigned to 'SPM44 Clash With Approved' (5 Apr 2027, 14:00-16:00).
Test Steps | 1. Click 'All Events' in the sidebar 2. Click 'SPM44 Clash With Approved' in the list 3. Click the 'Venue' tab 4. Click 'Search with filters' 5. Set the date and time filters to 5 Apr 2027, 14:00 to 16:00, then apply the filters
Test Data | Event: SPM44 Clash With Approved Filter window: 5 Apr 2027, 14:00-16:00
Expected Result | Step 5: 'SPM44 Conflict Room (SPM44-PLN)' is not among the results — the same conflict that refuses the request also keeps the room out of the search, so a coordinator is not offered a room they cannot have.
Created By | TAN JORDAN
Creation Date | 2026-10-02
Item
Actual Result | With the window set to 5 Apr 2027 14:00-16:00, 'SPM44 Conflict Room' was not among the results, while other rooms were still offered.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The search screen and the booking check now read the same rule - occupancyConflict() delegates to findVenueConflict(), so the two cannot disagree about whether a room is free.
Executed by | TAN JORDAN
Date of Execution | 2026-10-02
Item
Actual Result | With the window set to 5 Apr 2027 14:00-16:00, 'SPM44 Conflict Room' was not among the results, while other rooms were still offered.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The search screen and the booking check now read the same rule - occupancyConflict() delegates to findVenueConflict(), so the two cannot disagree about whether a room is free.
Executed by | Kayalvizhi
Date of Execution | 2026-10-03

## TC10
Item
Test Case ID | SPM-44-TC10
Pre-conditions | BLOCKED — there is no way to confirm a booking in the application. Venue Staff's 'Booking Requests' screen lists pending requests but has no Approve or Reject action; that belongs to Venue Booking Approval (SPM-43), which has no endpoint and no branch. The rule itself is implemented and unit tested in src/lib/venueConflict.ts (checkVenueBookingApproval, scope 'approved') — see open question 1.
Test Steps | 1. Log in as Venue Staff Marcus Wong (marcus.wong@connectsphere.com / password123) 2. Click 'Booking Requests' in the sidebar 3. Look for an Approve action on a pending request whose slot another approved booking already holds
Test Data | Blocked pending SPM-43 (Venue Booking Approval)
Expected Result | Step 3: No Approve action exists on the screen, so this criterion cannot be exercised through the application. When SPM-43 builds it, approving must be refused with the conflicting booking named, and the unit tests in src/lib/__tests__/venueConflict.test.ts already pin that behaviour.
Created By | TAN JORDAN
Creation Date | 2026-10-02
Item
Actual Result | Venue Staff's Booking Requests screen lists pending requests but carries no Approve and no Reject action - zero of each on the page - so there is no way to confirm a booking and the criterion cannot be exercised through the application.
Pass/Fail/Not Executed/Blocked | Blocked
Remarks | Blocked on SPM-43 (Venue Booking Approval), which has no endpoint and no branch. The rule itself is implemented and unit tested: checkVenueBookingApproval() in src/lib/venueConflict.ts, five tests in venueConflict.test.ts, including that a rival PENDING request must NOT block confirmation. See open question 1.
Executed by | TAN JORDAN
Date of Execution | 2026-10-02
Item
Actual Result | Step 3: No Approve action exists on the screen, so this criterion cannot be exercised through the application. When SPM-43 builds it, approving must be refused with the conflicting booking named, and the unit tests in src/lib/__tests__/venueConflict.test.ts already pin that behaviour.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | Was Blocked until SPM-43 (Review Venue Booking Request) merged to main on 2026-10-04. Merging also settled the duplication SPM-43 had flagged: approvalConflict() carried a second copy of the confirm-time rule and now calls findVenueConflict() with scope 'approved', so a rival PENDING request still does not block a decision. SPM-43's own unit tests pass unchanged, which is the evidence the delegation did not alter behaviour.
Executed by | Kayalvizhi
Date of Execution | 2026-10-04

## TC11
Item
Test Case ID | SPM-44-TC11
Pre-conditions | npm run fixtures:spm44 has been run. Orchard Seminar Room (ORC-SEM) records 60 minutes of setup and 30 of teardown, so a booking there takes one whole adjacent slot either side. 'SPM44 Midnight Holder' holds an APPROVED booking at ORC-SEM on 12 Apr 2027, Night (20:00-22:00) - Night is the last slot of its day, so its turnaround falls on the NEXT day's AM. 'SPM44 Midnight Clash' runs 13 Apr 2027 09:00-11:00 (AM). Logged in as Event Coordinator Daniel Tan (daniel.tan@connectsphere.com / password123), assigned to 'SPM44 Midnight Clash'.
Test Steps | 1. Click 'All Events' in the sidebar 2. Click 'SPM44 Midnight Clash' in the list 3. Click the 'Venue' tab 4. Find 'Orchard Seminar Room (ORC-SEM)' in the venue list and click its 'Request booking' button 5. Click 'Submit request'
Test Data | Event: SPM44 Midnight Clash (13 Apr 2027, 09:00-11:00, AM) Venue: Orchard Seminar Room (ORC-SEM), setup 60 min, teardown 30 min In the way: SPM44 Midnight Holder's approved booking the PREVIOUS evening (12 Apr 2027, Night), whose turnaround runs into 13 Apr AM
Expected Result | Step 4: The booking request screen opens with the Date 13 Apr 2027 and only 'AM (07:00–12:00)' ticked. Step 5: The request is refused, naming the booking from the previous evening and the 13 Apr AM slot it reaches into — the two events are on different calendar days and neither occupies the other's own slot, so this is the day-crossing half of AC2 (#123). No request is created.
Created By | TAN JORDAN
Creation Date | 2026-10-02
Item
Actual Result | The booking screen opened on 13 Apr 2027 with only AM ticked. Submitting was refused with 'Orchard Seminar Room is already booked for EVT-000864 SPM44 Midnight Holder on 12 Apr 2027 Night - 13 Apr 2027 AM.' No request was created.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The two events are on different calendar days and neither occupies the other's own slot: the clash exists only because the Night booking's turnaround runs into the next morning (#123). The message spans both days rather than naming one, which is what the day-crossing branch of the label was written for.
Executed by | TAN JORDAN
Date of Execution | 2026-10-02
Item
Actual Result | The booking screen opened on 13 Apr 2027 with only AM ticked. Submitting was refused with 'Orchard Seminar Room is already booked for EVT-000864 SPM44 Midnight Holder on 12 Apr 2027 Night - 13 Apr 2027 AM.' No request was created.
Pass/Fail/Not Executed/Blocked | Pass
Remarks | The two events are on different calendar days and neither occupies the other's own slot: the clash exists only because the Night booking's turnaround runs into the next morning (#123). The message spans both days rather than naming one, which is what the day-crossing branch of the label was written for.
Executed by | Kayalvizhi
Date of Execution | 2026-10-03