## Summary
Sprint 2 regression test
Process: docs/REGRESSION_TESTING.md. Yellow cells are for you to fill in; everything else is pre-filled or calculated.
Sprint | 2
Date tested
Tested by
Commit tested (main) |  | git rev-parse --short HEAD
Baseline | 586bd68 (last commit on main before Sprint 2 started, 21 Sep 2026)
Results | Retested cases | Smoke run | Automated checks
Total | 61 | 8 | 5
Pass | 0 | 0 | 0
Fail | 0 | 0 | 0
Changed by design | 0
Blocked | 0
Not run yet | 61 | 8 | 5
Result | Meaning |  |  | What to do
Pass | The app matches the expected result. |  |  | Nothing.
Fail | The app is wrong. |  |  | Raise a Jira bug linked to the story. Add a row to Follow-ups.
Changed by design | The app differs because a later story changed the behaviour on purpose. |  |  | Name that story in the notes. Add a row to Follow-ups so the test case gets updated.
Blocked | The case could not be run, for example because its test data no longer exists. |  |  | Say why in the notes. Add a row to Follow-ups.
Example of filled-in rows on 'Retested cases' (columns Result, Tested by, Date tested, Notes)
SPM-47-TC01 | Pass | Janelle | 2026-10-04
SPM-40-TC15 | Changed by design | Kristen | 2026-10-04 | SPM-54 added the 'Begin planning?' step. Case needs updating.
SPM-23-TC04 | Fail | Kristen | 2026-10-04 | Step 6: no confirmation message shown. Bug SPM-80.
Rules
Do not type results into the story workbooks in docs/test-cases/. They hold each story's original test run.
Never run npx prisma db seed. Use the script in the Test data column, before the story and after any case that changes data.
If a fix merges after a Fail, rerun the case and add a new row for it. Keep the Fail row.

## Retested cases
Sprint 2 regression: retested cases
Read the steps in the story workbook (docs/test-cases/). Record the result here, not in the workbook. Fill in the yellow cells.
Test case ID | Story | Title | Linked AC | Type | Workbook | Sheet | Test data | Result | Tested by | Date tested | Notes / bug key
SPM-21-TC01 | SPM-21 | Valid credentials sign the user in and open the dashboard | AC1 | Positive | SPM-21_Test_Cases.xlsx | TC01 | Base seed data
SPM-21-TC12 | SPM-21 | The signed-in user's role is named on the dashboard | AC3 | Positive | SPM-21_Test_Cases.xlsx | TC12 | Base seed data
SPM-22-TC01 | SPM-22 | An Attendee's sidebar offers only the Attendee screens | AC1 | Positive | SPM-22_Test_Cases.xlsx | TC01 | Base seed data
SPM-22-TC04 | SPM-22 | An Attendee opening an event sees only the Overview tab | AC2 | Positive | SPM-22_Test_Cases.xlsx | TC04 | Base seed data
SPM-22-TC17 | SPM-22 | Internal planning fields are absent from an Attendee's view of an event | AC5 | Positive | SPM-22_Test_Cases.xlsx | TC17 | Base seed data
SPM-22-TC19 | SPM-22 | The Operations Manager's navigation matches their permissions | AC6 | Positive | SPM-22_Test_Cases.xlsx | TC19 | Base seed data
SPM-23-TC01 | SPM-23 | Organiser can enter an event name and purpose | AC1 | Positive | SPM-23_Test_Cases.xlsx | TC01 | Base seed data
SPM-23-TC03 | SPM-23 | Organiser can enter and save an event description | AC2 | Positive | SPM-23_Test_Cases.xlsx | TC03 | Base seed data
SPM-23-TC04 | SPM-23 | Organiser can specify the proposed date and time | AC3 | Positive | SPM-23_Test_Cases.xlsx | TC04 | Base seed data
SPM-23-TC07 | SPM-23 | Organiser can specify expected attendance | AC4 | Positive | SPM-23_Test_Cases.xlsx | TC07 | Base seed data
SPM-23-TC10 | SPM-23 | Organiser can specify venue and accessibility requirements | AC5 | Positive | SPM-23_Test_Cases.xlsx | TC10 | Base seed data
SPM-23-TC18 | SPM-23 | A fully completed request can be submitted | AC7 | Positive | SPM-23_Test_Cases.xlsx | TC18 | Base seed data
SPM-23-TC27 | SPM-23 | A multi-session draft is identifiable as a draft and shows the span and largest attendance | AC6, AC8 | Positive | SPM-23_Test_Cases.xlsx | TC27 | Base seed data
SPM-24-TC01 | SPM-24 | Save Draft creates a saved draft with only a title | AC1 | Positive | SPM-24_Test_Cases.xlsx | TC01 | Base seed data |  |  |  | Run first: SPM-24-TC09 depends on it.
SPM-24-TC06 | SPM-24 | Organiser can leave and return to a saved draft | AC3 | Positive | SPM-24_Test_Cases.xlsx | TC06 | Base seed data
SPM-24-TC09 | SPM-24 | Editing a draft's fields saves the changes | AC4 | Positive | SPM-24_Test_Cases.xlsx | TC09 | Base seed data
SPM-24-TC14 | SPM-24 | A complete draft can be submitted and leaves draft status | AC1, AC5 | Positive | SPM-24_Test_Cases.xlsx | TC14 | Base seed data
SPM-25-TC01 | SPM-25 | Submitting a complete event request succeeds and moves it to Submitted | AC1, AC2 | Positive | SPM-25_Test_Cases.xlsx | TC01 | Base seed data
SPM-25-TC05 | SPM-25 | A submitted request no longer opens as an editable draft | AC3 | Positive | SPM-25_Test_Cases.xlsx | TC05 | Base seed data
SPM-25-TC06 | SPM-25 | Event Coordinator can see a submitted request in All Events | AC4 | Positive | SPM-25_Test_Cases.xlsx | TC06 | Base seed data
SPM-28-TC01 | SPM-28 | Review Queue lists only the Under review events assigned to the logged-in coordinator | AC1 | Positive | SPM-28_Test_Cases.xlsx | TC01 | npm run fixtures:spm28
SPM-28-TC05 | SPM-28 | Review page displays all requirements of the request | AC2 | Positive | SPM-28_Test_Cases.xlsx | TC05 | npm run fixtures:spm28
SPM-28-TC06 | SPM-28 | Missing information is clearly flagged on the review page | AC3 | Positive | SPM-28_Test_Cases.xlsx | TC06 | npm run fixtures:spm28
SPM-28-TC08 | SPM-28 | Coordinator approves a request for planning | AC4, AC6 | Positive | SPM-28_Test_Cases.xlsx | TC08 | npm run fixtures:spm28
SPM-28-TC10 | SPM-28 | Coordinator rejects a request with a reason | AC5, AC6 | Positive | SPM-28_Test_Cases.xlsx | TC10 | npm run fixtures:spm28
SPM-30-TC08 | SPM-30 | Ops Manager assigns a coordinator; it is recorded and the event moves to Under review | AC1, AC2, AC3 | Positive | SPM-30_Test_Cases.xlsx | TC08 | npm run fixtures:spm30
SPM-30-TC10 | SPM-30 | Owning organiser sees the assigned coordinator | AC5 | Positive | SPM-30_Test_Cases.xlsx | TC10 | npm run fixtures:spm30
SPM-30-TC13 | SPM-30 | Ops Manager reassigns an event from the event page | AC6, AC3 | Positive | SPM-30_Test_Cases.xlsx | TC13 | npm run fixtures:spm30 |  |  |  | Run first: SPM-30-TC14 depends on it.
SPM-30-TC14 | SPM-30 | After reassignment the previous coordinator loses access and the new one gains it | AC6, AC4 | Positive | SPM-30_Test_Cases.xlsx | TC14 | npm run fixtures:spm30
SPM-31-TC03 | SPM-31 | Opening a draft from 'My Events' goes straight to the draft editor, never the Overview tab | AC1 | Positive | SPM-31_Test_Cases.xlsx | TC03 | Base seed data
SPM-39-TC01 | SPM-39 | Venue Staff can create a venue record | AC1 | Positive | SPM-39_Test_Cases.xlsx | TC01 | Base seed data
SPM-39-TC05 | SPM-39 | Location, capacity, facilities and accessibility are all recorded and persist | AC2 | Positive | SPM-39_Test_Cases.xlsx | TC05 | Base seed data
SPM-39-TC07 | SPM-39 | Several layouts are recorded, each with its own capacity | AC3 | Positive | SPM-39_Test_Cases.xlsx | TC07 | Base seed data
SPM-39-TC10 | SPM-39 | Opening hours and turnaround times are recorded | AC4 | Positive | SPM-39_Test_Cases.xlsx | TC10 | Base seed data
SPM-39-TC13 | SPM-39 | Venue Staff can update an existing venue | AC5 | Positive | SPM-39_Test_Cases.xlsx | TC13 | Base seed data
SPM-39-TC15 | SPM-39 | A retired venue is no longer offered to a Coordinator | AC6 | Positive | SPM-39_Test_Cases.xlsx | TC15 | Base seed data
SPM-39-TC17 | SPM-39 | Reducing a layout below an approved booking's attendance flags that booking | AC7 | Positive | SPM-39_Test_Cases.xlsx | TC17 | Base seed data
SPM-40-TC13 | SPM-40 | All six filters combined, then Clear filters | AC1, AC2, AC3, AC4, AC5, AC6, AC7 | Positive | SPM-40_Test_Cases.xlsx | TC13 | Base seed data
SPM-41-TC05 | SPM-41 | The same attendance gets a different result under a different layout | AC1, AC4 | Positive | SPM-41_Test_Cases.xlsx | TC05 | Base seed data
SPM-41-TC06 | SPM-41 | Venue with all required facilities is suitable | AC2 | Positive | SPM-41_Test_Cases.xlsx | TC06 | Base seed data
SPM-41-TC09 | SPM-41 | Venue with all required accessibility features is suitable | AC3 | Positive | SPM-41_Test_Cases.xlsx | TC09 | Base seed data
SPM-42-TC01 | SPM-42 | Coordinator requests a suitable venue, with venue requirements and layout | AC1, AC6 | Positive | SPM-42_Test_Cases.xlsx | TC01 | npm run fixtures:spm42
SPM-42-TC04 | SPM-42 | An event with no sessions spanning AM and PM is requested on its own date and consumes both slots in full | AC2, AC4 | Positive | SPM-42_Test_Cases.xlsx | TC04 | npm run fixtures:spm42
SPM-42-TC09 | SPM-42 | A 3-session event gets one request per session, each using its session's date, time and layout | AC4, AC5 | Positive | SPM-42_Test_Cases.xlsx | TC09 | npm run fixtures:spm42 |  |  |  | Expected to differ once SPM-54 merges: first 'Submit request' on an Approved event now shows the 'Begin planning?' dialog.
SPM-42-TC11 | SPM-42 | The request reaches Venue Staff and shows Pending | AC7, AC8 | Positive | SPM-42_Test_Cases.xlsx | TC11 | npm run fixtures:spm42
SPM-46-TC01 | SPM-46 | Open a venue's availability and read the grid | AC1, AC2 | Positive | SPM-46_Test_Cases.xlsx | TC01 | Base seed data
SPM-46-TC09 | SPM-46 | Two overlapping unavailable periods are identified as overlapping | AC5 | Positive | SPM-46_Test_Cases.xlsx | TC09 | Base seed data
SPM-46-TC10 | SPM-46 | An Event Coordinator and an Operations Manager can open the calendar | AC6 | Positive | SPM-46_Test_Cases.xlsx | TC10 | Base seed data
SPM-46-TC12 | SPM-46 | An approved booking blocks its slots, and is listed, even while its event is still in planning | AC3, AC7 | Positive | SPM-46_Test_Cases.xlsx | TC12 | Base seed data
SPM-47-TC01 | SPM-47 | Coordinator records an equipment requirement with a type, quantity, and technical requirements | AC1, AC2, AC3 | Positive | SPM-47_Test_Cases.xlsx | TC01 | Base seed data
SPM-47-TC14 | SPM-47 | Organiser sees the same requirements read-only and cannot edit them | AC6, AC7 | Positive | SPM-47_Test_Cases.xlsx | TC14 | Base seed data
SPM-47-TC17 | SPM-47 | Coordinator scopes equipment requirements to individual sessions of a multi-session event | AC4, AC5 | Positive | SPM-47_Test_Cases.xlsx | TC17 | Base seed data
SPM-48-TC14 | SPM-48 | Two events on the same day can both be supported when stock covers both | AC4, AC5 | Positive | SPM-48_Test_Cases.xlsx | TC14 | Base seed data
SPM-48-TC15 | SPM-48 | Each session of a multi-session event is checked against its own dates | AC3, AC5 | Positive | SPM-48_Test_Cases.xlsx | TC15 | Base seed data
SPM-48-TC16 | SPM-48 | Equipment in ConnectSphere storage leaves the fixed transfer/prep time before the event | AC6 | Positive | SPM-48_Test_Cases.xlsx | TC16 | Base seed data
SPM-48-TC19 | SPM-48 | Units under maintenance are excluded from the available count | AC7 | Positive | SPM-48_Test_Cases.xlsx | TC19 | Base seed data
SPM-48-TC21 | SPM-48 | A request with several lines shows a result per line and one overall banner | AC2, AC8 | Positive | SPM-48_Test_Cases.xlsx | TC21 | Base seed data
SPM-49-TC01 | SPM-49 | Reserve the full requested quantity when enough is available | AC1 | Positive | SPM-49_Test_Cases.xlsx | TC01 | Base seed data
SPM-49-TC05 | SPM-49 | The reservation is still there, with its type and quantity, after reloading | AC2 | Positive | SPM-49_Test_Cases.xlsx | TC05 | Base seed data
SPM-49-TC19 | SPM-49 | Each session of a multi-session event is reserved against its own dates | AC3, AC4, AC5 | Positive | SPM-49_Test_Cases.xlsx | TC19 | Base seed data
SPM-49-TC20 | SPM-49 | A saved reservation can be viewed by another Technical Support user | AC6 | Positive | SPM-49_Test_Cases.xlsx | TC20 | Base seed data

## Automated checks
Sprint 2 regression: automated checks
Run on an up-to-date main. All five must pass before manual testing starts.
Check | Needs | Result | Run by | Date run | Notes
npm test | Nothing
npm run lint | Nothing
npm run build | Nothing
npm run verify:permissions | npm run dev in a second terminal
npm run verify:login | npm run dev in a second terminal

## Scope
Sprint 2 regression: scope
Prepared 2026-10-02 against main at 8cd0ba8, plus the SPM-54 branch (in review). Recheck after the last merge of the sprint.
Story | Title | Sprint | Changes counted since | In scope? | Reason | Cases selected
SPM-21 | User Login | 1 | End of Sprint 1 (586bd68) | Yes | Changed on main: src/app/dashboard/page.tsx, src/lib/apiAuth.ts Shared files changed: src/lib/permissions.ts, src/lib/roles.ts | 2
SPM-22 | Role-Based Access - UI Verification | 2 | No merge commit found; test cases written 2026-09-26 (22a8f04) | Yes | Changed on main: src/app/assignments/page.tsx, src/app/events/[id]/page.tsx, src/app/queue/page.tsx, src/app/venues/page.tsx Shared files changed: src/lib/eventTabs.ts, src/lib/permissions.ts, src/lib/roles.ts | 4
SPM-23 | Create Event Request | 1 | End of Sprint 1 (586bd68) | Yes | Changed on main: src/app/api/events/[id]/route.ts, src/app/api/events/route.ts, src/app/events/new/page.tsx, src/app/events/page.tsx, src/lib/validation/events.ts Shared files changed: prisma/schema.prisma, prisma/seed.ts | 7
SPM-24 | Save Draft Event Request | 1 | End of Sprint 1 (586bd68) | Yes | Changed on main: src/app/api/events/[id]/route.ts, src/app/api/events/route.ts, src/app/events/new/page.tsx, src/app/events/page.tsx Shared files changed: prisma/seed.ts, src/lib/statuses.ts | 4
SPM-25 | Submit Event Request | 1 | End of Sprint 1 (586bd68) | Yes | Changed on main: src/app/api/events/[id]/route.ts, src/app/events/new/page.tsx, src/app/events/page.tsx, src/lib/validation/events.ts Shared files changed: src/lib/permissions.ts, src/lib/roles.ts, src/lib/statuses.ts | 3
SPM-28 | Review Event Request | 2 | Story merged 2026-10-01 (4859afd) | Yes, once SPM-54 merges | Changed by SPM-54 (not merged yet): src/app/api/events/[id]/route.ts Shared files changed: prisma/seed.ts, src/lib/permissions.ts, src/lib/statuses.ts | 5
SPM-30 | Assign Event Coordinator | 2 | Story merged 2026-09-30 (1e4f40a) | Yes | Changed on main: src/app/api/events/[id]/route.ts, src/app/events/[id]/page.tsx Changed by SPM-54 (not merged yet): src/app/dashboard/page.tsx Shared files changed: prisma/seed.ts, src/lib/permissions.ts | 4
SPM-31 | View Event Information | 2 | Story merged 2026-09-25 (424dfff) | Yes | Changed on main: src/app/api/events/[id]/equipment/route.ts, src/app/api/events/[id]/route.ts, src/app/dashboard/page.tsx, src/app/events/[id]/page.tsx, src/app/events/new/page.tsx Changed by SPM-54 (not merged yet): src/app/api/events/[id]/equipment/[requestId]/route.ts Shared files changed: prisma/schema.prisma, prisma/seed.ts, src/lib/eventTabs.ts, src/lib/format.ts, src/lib/permissions.ts, src/lib/roles.ts, src/lib/statuses.ts | 1
SPM-39 | Manage Venue Catalogue | 1 | End of Sprint 1 (586bd68) | Yes | Changed on main: src/app/venues/[id]/edit/page.tsx, src/app/venues/page.tsx, src/lib/validation/venues.ts Shared files changed: prisma/schema.prisma, src/lib/permissions.ts | 7
SPM-40 | Search and Filter Suitable Venues | 2 | Story merged 2026-09-28 (053464e) | Yes | Changed on main: src/app/api/events/[id]/route.ts, src/app/events/[id]/venue/page.tsx, src/lib/validation/venues.ts Changed by SPM-54 (not merged yet): src/app/venues/search/page.tsx, src/lib/venueSearchForm.ts Shared files changed: prisma/seed.ts, src/lib/permissions.ts | 1
SPM-41 | Check Venue Suitability | 2 | Story merged 2026-09-27 (daf0788) | Yes | Changed on main: src/app/venues/page.tsx Shared files changed: prisma/schema.prisma, prisma/seed.ts | 3
SPM-42 | Request Venue Booking | 2 | Story merged 2026-10-01 (3f0f2e1) | Yes, once SPM-54 merges | Changed by SPM-54 (not merged yet): src/lib/venueBookingRequest.ts Shared files changed: prisma/seed.ts, src/lib/permissions.ts | 4
SPM-46 | View Venue Availability | 2 | Story merged 2026-09-28 (4df8f4d) | Yes | Changed on main: src/app/venues/page.tsx, src/lib/validation/venues.ts Shared files changed: src/lib/permissions.ts | 4
SPM-47 | Record Equipment Requirements | 1 | End of Sprint 1 (586bd68) | Yes | Changed on main: src/app/api/events/[id]/equipment/[requestId]/route.ts, src/app/api/events/[id]/equipment/route.ts, src/app/api/events/[id]/route.ts, src/app/events/[id]/equipment/page.tsx, src/app/events/[id]/page.tsx, src/lib/equipment.ts, src/lib/validation/equipment.ts Shared files changed: prisma/schema.prisma, src/lib/eventTabs.ts, src/lib/permissions.ts, src/lib/roles.ts | 3
SPM-48 | Check Equipment Availability | 2 | Story merged 2026-09-28 (deea1d4) | Yes | Changed on main: src/app/events/[id]/equipment/page.tsx | 5
SPM-49 | Reserve Equipment | 2 | Story merged 2026-09-28 (9bd17f3) | Yes | Changed on main: src/app/events/[id]/equipment/page.tsx Shared files changed: src/lib/permissions.ts | 4
SPM-54 | Begin Event Planning | 2 | In review, not merged yet | No | Finished this sprint; covered by its own test pass. | 0
Not listed: SPM-27, SPM-43, SPM-44 and SPM-50 are still in progress. If they merge before the sprint ends, they are tested by their own test cases this sprint, but check whether they change files that the stories above depend on.

## Smoke run
Sprint 2 regression: smoke run
Take one new event, titled 'REG S2 <your name>', through the whole flow. Do not use any story's fixture events.
Step | Role | What to do | Result | Tested by | Notes
1 | Event Organiser | Log in, create an event request, save it as a draft, reopen it and submit it.
2 | Event Operations Manager | Assign an Event Coordinator to the submitted request.
3 | Event Coordinator | Review and approve the request.
4 | Event Coordinator | Begin planning, search for a venue, check its availability and submit a venue booking request.
5 | Event Coordinator | Record the equipment required.
6 | Technical Support Staff | Check equipment availability and reserve it.
7 | Venue Staff | Open the venue list, edit a venue and view its availability calendar.
8 | Every role | Each role sees only its own sidebar links, and the organiser sees only their own events.

## Follow-ups
Sprint 2 regression: follow-ups
One row for each Fail (a bug) and each Changed by design or Blocked case (a test case to update).
Type | Test case ID | Jira key | Owner | What needs doing | Decision (fix now / next sprint) | Done?